## Cover
2023-04-05
Market Disciple
Financial Performance of Market Disciple - 04/03/2023

## Data-Practice
Project - Timesheet
Code | Project ID | Client Group | Client Detail | Category | Main focus | Secondary focus | Report | Slippage in start date | Days: Total | Days: PM | Days: PSO | Days: BA | Days: Developer | Days: Tester | Days: Contingency | Contingency
mdSOFT3187 Act | mdSOFT3187 | Retail | Retail | Wishlist | Technical Analysis | None | Actual | 3 | 21 | 3 | 2 | 3 | 12 | 1 | 0
mdSOFT3187 Bud | mdSOFT3187 | Retail | Retail | Wishlist | Technical Analysis | None | Budget | 0 | 24 | 3 | 2 | 3 | 15 | 1 | 0
mdSOFT3188 Act | mdSOFT3188 | Retail | Retail | Wishlist | Technical Analysis | None | Actual | 8 | 14 | 3 | 1 | 3 | 7 | 0 | 0
mdSOFT3188 Bud | mdSOFT3188 | Retail | Retail | Wishlist | Technical Analysis | None | Budget | 0 | 8 | 1 | 1 | 3 | 3 | 0 | 0
mdSOFT3189 Act | mdSOFT3189 | Retail | Retail | Wishlist | Technical Analysis | None | Actual | 7 | 25 | 5 | 1 | 1 | 15 | 3 | 0
mdSOFT3189 Bud | mdSOFT3189 | Retail | Retail | Wishlist | Technical Analysis | None | Budget | 0 | 24 | 3 | 2 | 1 | 15 | 3 | 0
mdSOFT3190 Act | mdSOFT3190 | Retail | Retail | Wishlist | Technical Analysis | None | Actual | 7 | 15 | 3 | 2 | 2 | 6 | 2 | 0
mdSOFT3190 Bud | mdSOFT3190 | Retail | Retail | Wishlist | Technical Analysis | None | Budget | 0 | 11 | 1 | 1 | 1 | 6 | 2 | 0
mdSOFT3191 Act | mdSOFT3191 | Retail | Retail | Wishlist | Technical Analysis | None | Actual | 7 | 10 | 1 | 2 | 2 | 3 | 2 | 0
mdSOFT3191 Bud | mdSOFT3191 | Retail | Retail | Wishlist | Technical Analysis | None | Budget | 0 | 13 | 1 | 2 | 2 | 7 | 1 | 0
mdSOFT3192 Act | mdSOFT3192 | Retail | Retail | Wishlist | Technical Analysis | None | Actual | 3 | 28 | 5 | 0 | 1 | 19 | 3 | 0
mdSOFT3192 Bud | mdSOFT3192 | Retail | Retail | Wishlist | Technical Analysis | None | Budget | 0 | 23 | 3 | 1 | 2 | 14 | 3 | 0
mdSOFT3193 Act | mdSOFT3193 | Retail | Retail | Wishlist | Technical Analysis | None | Actual | 6 | 7 | 1 | 2 | 1 | 3 | 0 | 0
mdSOFT3193 Bud | mdSOFT3193 | Retail | Retail | Wishlist | Technical Analysis | None | Budget | 0 | 5 | 1 | 2 | 0 | 2 | 0 | 0
mdSOFT3194 Act | mdSOFT3194 | Retail | Retail | Wishlist | Technical Analysis | None | Actual | 0 | 9 | 3 | 1 | 3 | 1 | 1 | 0
mdSOFT3194 Bud | mdSOFT3194 | Retail | Retail | Wishlist | Technical Analysis | None | Budget | 0 | 10 | 1 | 2 | 3 | 4 | 0 | 0
mdSOFT3195 Act | mdSOFT3195 | Retail | Retail | Wishlist | Technical Analysis | None | Actual | 5 | 26 | 4 | 3 | 2 | 13 | 4 | 0
mdSOFT3195 Bud | mdSOFT3195 | Retail | Retail | Wishlist | Technical Analysis | None | Budget | 0 | 20 | 2 | 2 | 1 | 12 | 3 | 0
mdSOFT3196 Act | mdSOFT3196 | Retail | Retail | Wishlist | Technical Analysis | None | Actual | 1 | 15 | 1 | 1 | 1 | 11 | 1 | 0
mdSOFT3196 Bud | mdSOFT3196 | Retail | Retail | Wishlist | Technical Analysis | None | Budget | 0 | 20 | 2 | 2 | 2 | 12 | 2 | 0
mdSOFT3197 Act | mdSOFT3197 | Retail | Retail | Wishlist | Technical Analysis | None | Actual | 10 | 9 | 2 | 0 | 1 | 4 | 2 | 0
mdSOFT3197 Bud | mdSOFT3197 | Retail | Retail | Wishlist | Technical Analysis | None | Budget | 0 | 13 | 2 | 1 | 1 | 8 | 1 | 0
mdSOFT3198 Act | mdSOFT3198 | Retail | Retail | Wishlist | Technical Analysis | None | Actual | 8 | 11 | 1 | 0 | 1 | 8 | 1 | 0
mdSOFT3198 Bud | mdSOFT3198 | Retail | Retail | Wishlist | Technical Analysis | None | Budget | 0 | 13 | 1 | 1 | 2 | 7 | 2 | 0
mdSOFT3199 Act | mdSOFT3199 | Retail | Retail | Wishlist | Technical Analysis | None | Actual | 4 | 18 | 1 | 2 | 1 | 13 | 1 | 0
mdSOFT3199 Bud | mdSOFT3199 | Retail | Retail | Wishlist | Technical Analysis | None | Budget | 0 | 21 | 3 | 2 | 1 | 14 | 1 | 0
mdSOFT3200 Act | mdSOFT3200 | Retail | Retail | Wishlist | Technical Analysis | None | Actual | 8 | 28 | 4 | 2 | 4 | 15 | 3 | 0
mdSOFT3200 Bud | mdSOFT3200 | Retail | Retail | Wishlist | Technical Analysis | None | Budget | 0 | 19 | 2 | 1 | 3 | 10 | 3 | 0
mdSOFT3201 Act | mdSOFT3201 | Retail | Retail | Wishlist | Technical Analysis | None | Actual | 10 | 21 | 2 | 0 | 2 | 15 | 2 | 0
mdSOFT3201 Bud | mdSOFT3201 | Retail | Retail | Wishlist | Technical Analysis | None | Budget | 0 | 20 | 2 | 1 | 3 | 12 | 2 | 0
mdSOFT3202 Act | mdSOFT3202 | Retail | Retail | Wishlist | Technical Analysis | None | Actual | 6 | 6 | 1 | 0 | 1 | 3 | 1 | 0
mdSOFT3202 Bud | mdSOFT3202 | Retail | Retail | Wishlist | Technical Analysis | None | Budget | 0 | 12 | 1 | 1 | 2 | 6 | 2 | 0
mdSOFT3203 Act | mdSOFT3203 | Retail | Retail | Wishlist | Technical Analysis | None | Actual | 2 | 14 | 1 | 2 | 0 | 11 | 0 | 0
mdSOFT3203 Bud | mdSOFT3203 | Retail | Retail | Wishlist | Technical Analysis | None | Budget | 0 | 11 | 1 | 1 | 1 | 7 | 1 | 0
mdSOFT3204 Act | mdSOFT3204 | Retail | Retail | Wishlist | Technical Analysis | None | Actual | 3 | 21 | 3 | 2 | 2 | 11 | 3 | 0
mdSOFT3204 Bud | mdSOFT3204 | Retail | Retail | Wishlist | Technical Analysis | None | Budget | 0 | 17 | 2 | 2 | 1 | 10 | 2 | 0
mdSOFT3205 Act | mdSOFT3205 | Retail | Retail | Wishlist | Technical Analysis | None | Actual | 5 | 7 | 3 | 0 | 1 | 3 | 0 | 0
mdSOFT3205 Bud | mdSOFT3205 | Retail | Retail | Wishlist | Technical Analysis | None | Budget | 0 | 11 | 1 | 1 | 2 | 6 | 1 | 0
mdSOFT3206 Act | mdSOFT3206 | Retail | Retail | Wishlist | Technical Analysis | None | Actual | 0 | 3 | 1 | 0 | 0 | 2 | 0 | 0
mdSOFT3206 Bud | mdSOFT3206 | Retail | Retail | Wishlist | Technical Analysis | None | Budget | 0 | 3 | 1 | 1 | 0 | 1 | 0 | 0
mdSOFT3207 Act | mdSOFT3207 | Retail | Retail | Wishlist | Technical Analysis | None | Actual | 8 | 16 | 2 | 2 | 3 | 8 | 1 | 0
mdSOFT3207 Bud | mdSOFT3207 | Retail | Retail | Wishlist | Technical Analysis | None | Budget | 0 | 7 | 1 | 1 | 2 | 3 | 0 | 0
mdSOFT3208 Act | mdSOFT3208 | Retail | Retail | Wishlist | Fundamental Analysis | None | Actual | 7 | 7 | 1 | 2 | 1 | 2 | 1 | 0
mdSOFT3208 Bud | mdSOFT3208 | Retail | Retail | Wishlist | Fundamental Analysis | None | Budget | 0 | 8 | 1 | 2 | 1 | 4 | 0 | 0
mdSOFT3209 Act | mdSOFT3209 | Retail | Retail | Wishlist | Fundamental Analysis | None | Actual | 9 | 17 | 1 | 1 | 1 | 12 | 2 | 0
mdSOFT3209 Bud | mdSOFT3209 | Retail | Retail | Wishlist | Fundamental Analysis | None | Budget | 0 | 18 | 2 | 2 | 2 | 11 | 1 | 0
mdSOFT3210 Act | mdSOFT3210 | Retail | Retail | Wishlist | Fundamental Analysis | None | Actual | 5 | 15 | 1 | 2 | 0 | 10 | 2 | 0
mdSOFT3210 Bud | mdSOFT3210 | Retail | Retail | Wishlist | Fundamental Analysis | None | Budget | 0 | 22 | 3 | 2 | 1 | 14 | 2 | 0
mdSOFT3211 Act | mdSOFT3211 | Retail | Retail | Wishlist | Fundamental Analysis | None | Actual | 8 | 16 | 1 | 2 | 1 | 9 | 3 | 0
mdSOFT3211 Bud | mdSOFT3211 | Retail | Retail | Wishlist | Fundamental Analysis | None | Budget | 0 | 19 | 2 | 1 | 1 | 12 | 3 | 0
mdSOFT3212 Act | mdSOFT3212 | Retail | Retail | Wishlist | Fundamental Analysis | None | Actual | 7 | 12 | 1 | 1 | 1 | 8 | 1 | 0
mdSOFT3212 Bud | mdSOFT3212 | Retail | Retail | Wishlist | Fundamental Analysis | None | Budget | 0 | 13 | 1 | 2 | 2 | 7 | 1 | 0
mdSOFT3213 Act | mdSOFT3213 | Retail | Retail | Wishlist | Fundamental Analysis | None | Actual | 4 | 21 | 4 | 1 | 2 | 13 | 1 | 0
mdSOFT3213 Bud | mdSOFT3213 | Retail | Retail | Wishlist | Fundamental Analysis | None | Budget | 0 | 17 | 2 | 1 | 2 | 11 | 1 | 0
mdSOFT3214 Act | mdSOFT3214 | Retail | Retail | Wishlist | Fundamental Analysis | None | Actual | 0 | 12 | 1 | 2 | 4 | 5 | 0 | 0
mdSOFT3214 Bud | mdSOFT3214 | Retail | Retail | Wishlist | Fundamental Analysis | None | Budget | 0 | 9 | 1 | 2 | 3 | 3 | 0 | 0
mdSOFT3215 Act | mdSOFT3215 | Retail | Retail | Wishlist | Fundamental Analysis | None | Actual | 3 | 16 | 1 | 1 | 1 | 10 | 3 | 0
mdSOFT3215 Bud | mdSOFT3215 | Retail | Retail | Wishlist | Fundamental Analysis | None | Budget | 0 | 12 | 1 | 2 | 2 | 5 | 2 | 0
mdSOFT3216 Act | mdSOFT3216 | Retail | Retail | Wishlist | Fundamental Analysis | None | Actual | 2 | 6 | 1 | 0 | 3 | 1 | 1 | 0
mdSOFT3216 Bud | mdSOFT3216 | Retail | Retail | Wishlist | Fundamental Analysis | None | Budget | 0 | 11 | 1 | 1 | 2 | 5 | 2 | 0
mdSOFT3217 Act | mdSOFT3217 | Retail | Retail | Wishlist | Fundamental Analysis | None | Actual | 7 | 9 | 1 | 1 | 2 | 4 | 1 | 0
mdSOFT3217 Bud | mdSOFT3217 | Retail | Retail | Wishlist | Fundamental Analysis | None | Budget | 0 | 17 | 2 | 2 | 2 | 9 | 2 | 0
mdSOFT3218 Act | mdSOFT3218 | Retail | Retail | Wishlist | Fundamental Analysis | None | Actual | 4 | 26 | 4 | 0 | 3 | 15 | 4 | 0
mdSOFT3218 Bud | mdSOFT3218 | Retail | Retail | Wishlist | Fundamental Analysis | None | Budget | 0 | 19 | 2 | 1 | 2 | 11 | 3 | 0
mdSOFT3219 Act | mdSOFT3219 | Retail | Retail | Wishlist | Fundamental Analysis | None | Actual | 6 | 14 | 2 | 0 | 3 | 9 | 0 | 0
mdSOFT3219 Bud | mdSOFT3219 | Retail | Retail | Wishlist | Fundamental Analysis | None | Budget | 0 | 8 | 1 | 1 | 2 | 4 | 0 | 0
mdSOFT3220 Act | mdSOFT3220 | Retail | Retail | Wishlist | Fundamental Analysis | None | Actual | 8 | 22 | 1 | 1 | 1 | 17 | 2 | 0
mdSOFT3220 Bud | mdSOFT3220 | Retail | Retail | Wishlist | Fundamental Analysis | None | Budget | 0 | 19 | 3 | 1 | 1 | 13 | 1 | 0
mdSOFT3221 Act | mdSOFT3221 | Retail | Retail | Wishlist | Inter-Market Analysis | None | Actual | 3 | 17 | 4 | 0 | 1 | 11 | 1 | 0
mdSOFT3221 Bud | mdSOFT3221 | Retail | Retail | Wishlist | Inter-Market Analysis | None | Budget | 0 | 22 | 3 | 1 | 1 | 15 | 2 | 0
mdSOFT3222 Act | mdSOFT3222 | Retail | Retail | Wishlist | Inter-Market Analysis | None | Actual | 9 | 20 | 4 | 0 | 2 | 12 | 2 | 0
mdSOFT3222 Bud | mdSOFT3222 | Retail | Retail | Wishlist | Inter-Market Analysis | None | Budget | 0 | 15 | 2 | 1 | 3 | 8 | 1 | 0
mdSOFT3223 Act | mdSOFT3223 | Retail | Retail | Wishlist | Inter-Market Analysis | None | Actual | 10 | 9 | 1 | 0 | 3 | 5 | 0 | 0
mdSOFT3223 Bud | mdSOFT3223 | Retail | Retail | Wishlist | Inter-Market Analysis | None | Budget | 0 | 7 | 1 | 1 | 2 | 3 | 0 | 0
mdSOFT3224 Act | mdSOFT3224 | Retail | Retail | Wishlist | Inter-Market Analysis | None | Actual | 7 | 16 | 1 | 3 | 2 | 8 | 2 | 0
mdSOFT3224 Bud | mdSOFT3224 | Retail | Retail | Wishlist | Inter-Market Analysis | None | Budget | 0 | 12 | 1 | 2 | 1 | 7 | 1 | 0
mdSOFT3225 Act | mdSOFT3225 | Retail | Retail | Wishlist | Inter-Market Analysis | None | Actual | 1 | 23 | 1 | 1 | 3 | 16 | 2 | 0
mdSOFT3225 Bud | mdSOFT3225 | Retail | Retail | Wishlist | Inter-Market Analysis | None | Budget | 0 | 20 | 2 | 1 | 3 | 12 | 2 | 0
mdSOFT3226 Act | mdSOFT3226 | Retail | Retail | Wishlist | Quantitative Analysis | None | Actual | 4 | 23 | 5 | 1 | 2 | 13 | 2 | 0
mdSOFT3226 Bud | mdSOFT3226 | Retail | Retail | Wishlist | Quantitative Analysis | None | Budget | 0 | 24 | 3 | 2 | 2 | 15 | 2 | 0
mdSOFT3227 Act | mdSOFT3227 | Retail | Retail | Wishlist | Quantitative Analysis | None | Actual | 2 | 10 | 1 | 2 | 1 | 6 | 0 | 0
mdSOFT3227 Bud | mdSOFT3227 | Retail | Retail | Wishlist | Quantitative Analysis | None | Budget | 0 | 9 | 1 | 1 | 1 | 5 | 1 | 0
mdSOFT3228 Act | mdSOFT3228 | Institutional | Retail | Enhancement | Technical Analysis | None | Actual | 3 | 16 | 1 | 1 | 4 | 9 | 1 | 0
mdSOFT3228 Bud | mdSOFT3228 | Institutional | Retail | Enhancement | Technical Analysis | None | Budget | 0 | 17 | 3 | 1 | 2 | 7 | 2 | 2
mdSOFT3229 Act | mdSOFT3229 | Institutional | Bank | Enhancement | Technical Analysis | None | Actual | 7 | 25 | 4 | 4 | 2 | 11 | 4 | 0
mdSOFT3229 Bud | mdSOFT3229 | Institutional | Bank | Enhancement | Technical Analysis | None | Budget | 0 | 17 | 3 | 2 | 1 | 7 | 2 | 2
mdSOFT3230 Act | mdSOFT3230 | Institutional | Asset Manager | Enhancement | Technical Analysis | None | Actual | 2 | 28 | 6 | 6 | 2 | 9 | 5 | 0
mdSOFT3230 Bud | mdSOFT3230 | Institutional | Asset Manager | Enhancement | Technical Analysis | None | Budget | 0 | 38 | 5 | 6 | 4 | 15 | 4 | 4
mdSOFT3231 Act | mdSOFT3231 | Institutional | Broker | Enhancement | Fundamental Analysis | None | Actual | 8 | 11 | 2 | 1 | 3 | 4 | 1 | 0
mdSOFT3231 Bud | mdSOFT3231 | Institutional | Broker | Enhancement | Fundamental Analysis | None | Budget | 0 | 18 | 3 | 2 | 1 | 8 | 2 | 2
mdSOFT3232 Act | mdSOFT3232 | Institutional | Asset Manager | Enhancement | Fundamental Analysis | None | Actual | 13 | 27 | 3 | 5 | 6 | 8 | 5 | 0
mdSOFT3232 Bud | mdSOFT3232 | Institutional | Asset Manager | Enhancement | Fundamental Analysis | None | Budget | 0 | 28 | 4 | 3 | 5 | 10 | 3 | 3
mdSOFT3233 Act | mdSOFT3233 | Institutional | Retail | Enhancement | Fundamental Analysis | None | Actual | 18 | 35 | 5 | 6 | 2 | 16 | 6 | 0
mdSOFT3233 Bud | mdSOFT3233 | Institutional | Retail | Enhancement | Fundamental Analysis | None | Budget | 0 | 44 | 7 | 6 | 4 | 18 | 5 | 4
mdSOFT3234 Act | mdSOFT3234 | Institutional | Hedge Fund | Enhancement | Fundamental Analysis | None | Actual | 3 | 22 | 5 | 3 | 3 | 7 | 4 | 0
mdSOFT3234 Bud | mdSOFT3234 | Institutional | Hedge Fund | Enhancement | Fundamental Analysis | None | Budget | 0 | 16 | 2 | 1 | 2 | 7 | 2 | 2
mdSOFT3235 Act | mdSOFT3235 | Institutional | Bank | Enhancement | Fundamental Analysis | None | Actual | 10 | 16 | 3 | 1 | 1 | 8 | 3 | 0
mdSOFT3235 Bud | mdSOFT3235 | Institutional | Bank | Enhancement | Fundamental Analysis | None | Budget | 0 | 17 | 3 | 2 | 2 | 7 | 1 | 2
mdSOFT3236 Act | mdSOFT3236 | Institutional | Hedge Fund | Enhancement | Fundamental Analysis | None | Actual | 20 | 20 | 4 | 2 | 4 | 6 | 4 | 0
mdSOFT3236 Bud | mdSOFT3236 | Institutional | Hedge Fund | Enhancement | Fundamental Analysis | None | Budget | 0 | 15 | 2 | 2 | 2 | 5 | 2 | 2
mdSOFT3237 Act | mdSOFT3237 | Institutional | Bank | Enhancement | Fundamental Analysis | None | Actual | 8 | 40 | 6 | 4 | 3 | 20 | 7 | 0
mdSOFT3237 Bud | mdSOFT3237 | Institutional | Bank | Enhancement | Fundamental Analysis | None | Budget | 0 | 44 | 6 | 6 | 5 | 18 | 5 | 4
mdSOFT3238 Act | mdSOFT3238 | Institutional | Bank | Enhancement | Fundamental Analysis | None | Actual | 16 | 23 | 4 | 3 | 4 | 9 | 3 | 0
mdSOFT3238 Bud | mdSOFT3238 | Institutional | Bank | Enhancement | Fundamental Analysis | None | Budget | 0 | 36 | 6 | 4 | 4 | 14 | 4 | 4
mdSOFT3239 Act | mdSOFT3239 | Institutional | Retail | Enhancement | Inter-Market Analysis | None | Actual | 7 | 21 | 1 | 2 | 2 | 15 | 1 | 0
mdSOFT3239 Bud | mdSOFT3239 | Institutional | Retail | Enhancement | Inter-Market Analysis | None | Budget | 0 | 13 | 2 | 2 | 1 | 5 | 1 | 2
mdSOFT3240 Act | mdSOFT3240 | Institutional | Bank | Enhancement | Inter-Market Analysis | None | Actual | 9 | 10 | 1 | 2 | 1 | 3 | 3 | 0
mdSOFT3240 Bud | mdSOFT3240 | Institutional | Bank | Enhancement | Inter-Market Analysis | None | Budget | 0 | 14 | 2 | 1 | 2 | 5 | 2 | 2
mdSOFT3241 Act | mdSOFT3241 | Institutional | Hedge Fund | Enhancement | Inter-Market Analysis | None | Actual | 11 | 35 | 7 | 4 | 3 | 18 | 3 | 0
mdSOFT3241 Bud | mdSOFT3241 | Institutional | Hedge Fund | Enhancement | Inter-Market Analysis | None | Budget | 0 | 35 | 5 | 3 | 5 | 14 | 4 | 4
mdSOFT3242 Act | mdSOFT3242 | Institutional | Broker | Enhancement | Inter-Market Analysis | None | Actual | 21 | 51 | 10 | 5 | 7 | 23 | 6 | 0
mdSOFT3242 Bud | mdSOFT3242 | Institutional | Broker | Enhancement | Inter-Market Analysis | None | Budget | 0 | 49 | 8 | 6 | 5 | 21 | 4 | 5
mdSOFT3243 Act | mdSOFT3243 | Institutional | Bank | Enhancement | Quantitative Analysis | None | Actual | 5 | 16 | 4 | 1 | 4 | 3 | 4 | 0
mdSOFT3243 Bud | mdSOFT3243 | Institutional | Bank | Enhancement | Quantitative Analysis | None | Budget | 0 | 17 | 3 | 2 | 2 | 6 | 2 | 2
mdSOFT3244 Act | mdSOFT3244 | Institutional | Asset Manager | Enhancement | Quantitative Analysis | None | Actual | 15 | 21 | 3 | 4 | 3 | 8 | 3 | 0
mdSOFT3244 Bud | mdSOFT3244 | Institutional | Asset Manager | Enhancement | Quantitative Analysis | None | Budget | 0 | 32 | 5 | 4 | 5 | 12 | 3 | 3
mdSOFT3245 Act | mdSOFT3245 | Institutional | Hedge Fund | Enhancement | Quantitative Analysis | None | Actual | 14 | 42 | 5 | 5 | 4 | 22 | 6 | 0
mdSOFT3245 Bud | mdSOFT3245 | Institutional | Hedge Fund | Enhancement | Quantitative Analysis | None | Budget | 0 | 38 | 5 | 5 | 3 | 16 | 5 | 4
mdSOFT3246 Act | mdSOFT3246 | Institutional | Hedge Fund | Enhancement | Quantitative Analysis | None | Actual | 18 | 24 | 5 | 4 | 1 | 11 | 3 | 0
mdSOFT3246 Bud | mdSOFT3246 | Institutional | Hedge Fund | Enhancement | Quantitative Analysis | None | Budget | 0 | 18 | 3 | 2 | 1 | 8 | 2 | 2
mdSOFT3247 Act | mdSOFT3247 | Institutional | Bank | Enhancement | Quantitative Analysis | None | Actual | 3 | 39 | 4 | 6 | 6 | 18 | 5 | 0
mdSOFT3247 Bud | mdSOFT3247 | Institutional | Bank | Enhancement | Quantitative Analysis | None | Budget | 0 | 31 | 4 | 4 | 5 | 12 | 3 | 3
mdSOFT3248 Act | mdSOFT3248 | Institutional | Asset Manager | Enhancement | Quantitative Analysis | None | Actual | 5 | 33 | 4 | 5 | 5 | 15 | 4 | 0
mdSOFT3248 Bud | mdSOFT3248 | Institutional | Asset Manager | Enhancement | Quantitative Analysis | None | Budget | 0 | 39 | 5 | 6 | 4 | 16 | 4 | 4
mdSOFT3249 Act | mdSOFT3249 | Institutional | Hedge Fund | Enhancement | Quantitative Analysis | None | Actual | 10 | 26 | 4 | 6 | 6 | 5 | 5 | 0
mdSOFT3249 Bud | mdSOFT3249 | Institutional | Hedge Fund | Enhancement | Quantitative Analysis | None | Budget | 0 | 38 | 5 | 6 | 4 | 15 | 4 | 4
mdSOFT3250 Act | mdSOFT3250 | Institutional | Hedge Fund | Enhancement | Quantitative Analysis | None | Actual | 3 | 41 | 6 | 4 | 5 | 20 | 6 | 0
mdSOFT3250 Bud | mdSOFT3250 | Institutional | Hedge Fund | Enhancement | Quantitative Analysis | None | Budget | 0 | 42 | 6 | 5 | 3 | 20 | 4 | 4
mdSOFT3251 Act | mdSOFT3251 | Institutional | Asset Manager | Enhancement | Quantitative Analysis | None | Actual | 13 | 29 | 2 | 4 | 2 | 18 | 3 | 0
mdSOFT3251 Bud | mdSOFT3251 | Institutional | Asset Manager | Enhancement | Quantitative Analysis | None | Budget | 0 | 27 | 4 | 4 | 3 | 10 | 3 | 3
mdSOFT3252 Act | mdSOFT3252 | Institutional | Bank | Implementation | Technical Analysis | None | Actual | 28 | 398 | 35 | 81 | 27 | 238 | 17 | 0
mdSOFT3252 Bud | mdSOFT3252 | Institutional | Bank | Implementation | Technical Analysis | None | Budget | 0 | 362 | 40 | 67 | 17 | 191 | 14 | 33
mdSOFT3253 Act | mdSOFT3253 | Institutional | Retail | Implementation | Technical Analysis | None | Actual | 40 | 576 | 88 | 124 | 25 | 326 | 13 | 0
mdSOFT3253 Bud | mdSOFT3253 | Institutional | Retail | Implementation | Technical Analysis | None | Budget | 0 | 583 | 69 | 99 | 20 | 329 | 13 | 53
mdSOFT3254 Act | mdSOFT3254 | Institutional | Asset Manager | Implementation | Technical Analysis | None | Actual | 17 | 366 | 64 | 90 | 12 | 194 | 6 | 0
mdSOFT3254 Bud | mdSOFT3254 | Institutional | Asset Manager | Implementation | Technical Analysis | None | Budget | 0 | 402 | 60 | 73 | 16 | 208 | 8 | 37
mdSOFT3255 Act | mdSOFT3255 | Institutional | Bank | Implementation | Technical Analysis | Inter-Market Analysis | Actual | 20 | 501 | 86 | 87 | 16 | 299 | 13 | 0
mdSOFT3255 Bud | mdSOFT3255 | Institutional | Bank | Implementation | Technical Analysis | Inter-Market Analysis | Budget | 0 | 555 | 92 | 83 | 12 | 307 | 10 | 51
mdSOFT3256 Act | mdSOFT3256 | Institutional | Asset Manager | Implementation | Technical Analysis | None | Actual | 33 | 352 | 56 | 42 | 15 | 227 | 12 | 0
mdSOFT3256 Bud | mdSOFT3256 | Institutional | Asset Manager | Implementation | Technical Analysis | None | Budget | 0 | 315 | 38 | 48 | 13 | 179 | 8 | 29
mdSOFT3257 Act | mdSOFT3257 | Institutional | Broker | Implementation | Technical Analysis | None | Actual | 14 | 357 | 55 | 84 | 11 | 199 | 8 | 0
mdSOFT3257 Bud | mdSOFT3257 | Institutional | Broker | Implementation | Technical Analysis | None | Budget | 0 | 361 | 55 | 59 | 10 | 197 | 7 | 33
mdSOFT3258 Act | mdSOFT3258 | Institutional | Hedge Fund | Implementation | Technical Analysis | Quantitative Analysis | Actual | 23 | 518 | 79 | 88 | 24 | 312 | 15 | 0
mdSOFT3258 Bud | mdSOFT3258 | Institutional | Hedge Fund | Implementation | Technical Analysis | Quantitative Analysis | Budget | 0 | 469 | 66 | 68 | 17 | 263 | 12 | 43
mdSOFT3259 Act | mdSOFT3259 | Institutional | Bank | Implementation | Fundamental Analysis | Technical Analysis | Actual | 4 | 354 | 58 | 66 | 16 | 194 | 20 | 0
mdSOFT3259 Bud | mdSOFT3259 | Institutional | Bank | Implementation | Fundamental Analysis | Technical Analysis | Budget | 0 | 374 | 51 | 65 | 10 | 198 | 16 | 34
mdSOFT3260 Act | mdSOFT3260 | Institutional | Asset Manager | Implementation | Fundamental Analysis | None | Actual | 38 | 412 | 75 | 86 | 20 | 224 | 7 | 0
mdSOFT3260 Bud | mdSOFT3260 | Institutional | Asset Manager | Implementation | Fundamental Analysis | None | Budget | 0 | 442 | 55 | 78 | 12 | 251 | 5 | 41
mdSOFT3261 Act | mdSOFT3261 | Institutional | Asset Manager | Implementation | Fundamental Analysis | Quantitative Analysis | Actual | 42 | 463 | 58 | 102 | 12 | 283 | 8 | 0
mdSOFT3261 Bud | mdSOFT3261 | Institutional | Asset Manager | Implementation | Fundamental Analysis | Quantitative Analysis | Budget | 0 | 415 | 47 | 80 | 10 | 235 | 5 | 38
mdSOFT3262 Act | mdSOFT3262 | Institutional | Asset Manager | Implementation | Fundamental Analysis | None | Actual | 34 | 360 | 62 | 64 | 7 | 220 | 7 | 0
mdSOFT3262 Bud | mdSOFT3262 | Institutional | Asset Manager | Implementation | Fundamental Analysis | None | Budget | 0 | 352 | 55 | 53 | 12 | 191 | 9 | 32
mdSOFT3263 Act | mdSOFT3263 | Institutional | Bank | Implementation | Fundamental Analysis | None | Actual | 11 | 591 | 81 | 135 | 14 | 337 | 24 | 0
mdSOFT3263 Bud | mdSOFT3263 | Institutional | Bank | Implementation | Fundamental Analysis | None | Budget | 0 | 633 | 77 | 111 | 19 | 348 | 20 | 58
mdSOFT3264 Act | mdSOFT3264 | Institutional | Retail | Implementation | Fundamental Analysis | Inter-Market Analysis | Actual | 3 | 378 | 71 | 95 | 7 | 198 | 7 | 0
mdSOFT3264 Bud | mdSOFT3264 | Institutional | Retail | Implementation | Fundamental Analysis | Inter-Market Analysis | Budget | 0 | 356 | 54 | 65 | 10 | 186 | 8 | 33
mdSOFT3265 Act | mdSOFT3265 | Institutional | Bank | Implementation | Fundamental Analysis | None | Actual | 1 | 393 | 51 | 59 | 21 | 250 | 12 | 0
mdSOFT3265 Bud | mdSOFT3265 | Institutional | Bank | Implementation | Fundamental Analysis | None | Budget | 0 | 465 | 57 | 68 | 12 | 271 | 14 | 43
mdSOFT3266 Act | mdSOFT3266 | Institutional | Hedge Fund | Implementation | Fundamental Analysis | Inter-Market Analysis | Actual | 32 | 418 | 64 | 91 | 19 | 234 | 10 | 0
mdSOFT3266 Bud | mdSOFT3266 | Institutional | Hedge Fund | Implementation | Fundamental Analysis | Inter-Market Analysis | Budget | 0 | 359 | 56 | 61 | 10 | 192 | 7 | 33
mdSOFT3267 Act | mdSOFT3267 | Institutional | Asset Manager | Implementation | Fundamental Analysis | Technical Analysis | Actual | 17 | 389 | 47 | 65 | 21 | 236 | 20 | 0
mdSOFT3267 Bud | mdSOFT3267 | Institutional | Asset Manager | Implementation | Fundamental Analysis | Technical Analysis | Budget | 0 | 388 | 54 | 54 | 19 | 206 | 19 | 36
mdSOFT3268 Act | mdSOFT3268 | Institutional | Broker | Implementation | Inter-Market Analysis | Technical Analysis | Actual | 32 | 394 | 72 | 70 | 23 | 210 | 19 | 0
mdSOFT3268 Bud | mdSOFT3268 | Institutional | Broker | Implementation | Inter-Market Analysis | Technical Analysis | Budget | 0 | 363 | 53 | 51 | 20 | 189 | 17 | 33
mdSOFT3269 Act | mdSOFT3269 | Institutional | Bank | Implementation | Inter-Market Analysis | Fundamental Analysis | Actual | 23 | 567 | 106 | 94 | 16 | 331 | 20 | 0
mdSOFT3269 Bud | mdSOFT3269 | Institutional | Bank | Implementation | Inter-Market Analysis | Fundamental Analysis | Budget | 0 | 557 | 91 | 79 | 13 | 304 | 19 | 51
mdSOFT3270 Act | mdSOFT3270 | Institutional | Bank | Implementation | Inter-Market Analysis | Quantitative Analysis | Actual | 3 | 543 | 109 | 80 | 17 | 332 | 5 | 0
mdSOFT3270 Bud | mdSOFT3270 | Institutional | Bank | Implementation | Inter-Market Analysis | Quantitative Analysis | Budget | 0 | 599 | 92 | 88 | 18 | 339 | 7 | 55
mdSOFT3271 Act | mdSOFT3271 | Institutional | Retail | Implementation | Inter-Market Analysis | Quantitative Analysis | Actual | 42 | 606 | 102 | 105 | 18 | 365 | 16 | 0
mdSOFT3271 Bud | mdSOFT3271 | Institutional | Retail | Implementation | Inter-Market Analysis | Quantitative Analysis | Budget | 0 | 625 | 100 | 106 | 16 | 332 | 14 | 57
mdSOFT3272 Act | mdSOFT3272 | Institutional | Asset Manager | Implementation | Inter-Market Analysis | None | Actual | 22 | 368 | 36 | 57 | 23 | 231 | 21 | 0
mdSOFT3272 Bud | mdSOFT3272 | Institutional | Asset Manager | Implementation | Inter-Market Analysis | None | Budget | 0 | 329 | 39 | 46 | 13 | 185 | 16 | 30
mdSOFT3273 Act | mdSOFT3273 | Institutional | Retail | Implementation | Inter-Market Analysis | Fundamental Analysis | Actual | 18 | 455 | 56 | 83 | 23 | 272 | 21 | 0
mdSOFT3273 Bud | mdSOFT3273 | Institutional | Retail | Implementation | Inter-Market Analysis | Fundamental Analysis | Budget | 0 | 468 | 53 | 69 | 17 | 266 | 20 | 43
mdSOFT3274 Act | mdSOFT3274 | Institutional | Broker | Implementation | Quantitative Analysis | Fundamental Analysis | Actual | 10 | 541 | 87 | 104 | 13 | 324 | 13 | 0
mdSOFT3274 Bud | mdSOFT3274 | Institutional | Broker | Implementation | Quantitative Analysis | Fundamental Analysis | Budget | 0 | 560 | 80 | 83 | 18 | 319 | 9 | 51
mdSOFT3275 Act | mdSOFT3275 | Institutional | Asset Manager | Implementation | Quantitative Analysis | Fundamental Analysis | Actual | 26 | 340 | 54 | 76 | 10 | 180 | 20 | 0
mdSOFT3275 Bud | mdSOFT3275 | Institutional | Asset Manager | Implementation | Quantitative Analysis | Fundamental Analysis | Budget | 0 | 321 | 42 | 57 | 14 | 163 | 15 | 30
mdSOFT3276 Act | mdSOFT3276 | Institutional | Bank | Implementation | Quantitative Analysis | Fundamental Analysis | Actual | 5 | 451 | 86 | 84 | 11 | 266 | 4 | 0
mdSOFT3276 Bud | mdSOFT3276 | Institutional | Bank | Implementation | Quantitative Analysis | Fundamental Analysis | Budget | 0 | 494 | 73 | 76 | 13 | 282 | 5 | 45
mdSOFT3277 Act | mdSOFT3277 | Institutional | Asset Manager | Implementation | Quantitative Analysis | Technical Analysis | Actual | 17 | 424 | 65 | 78 | 22 | 250 | 9 | 0
mdSOFT3277 Bud | mdSOFT3277 | Institutional | Asset Manager | Implementation | Quantitative Analysis | Technical Analysis | Budget | 0 | 473 | 73 | 81 | 14 | 252 | 10 | 43
mdSOFT3278 Act | mdSOFT3278 | Institutional | Asset Manager | Implementation | Quantitative Analysis | None | Actual | 35 | 539 | 76 | 95 | 9 | 353 | 6 | 0
mdSOFT3278 Bud | mdSOFT3278 | Institutional | Asset Manager | Implementation | Quantitative Analysis | None | Budget | 0 | 546 | 79 | 82 | 13 | 316 | 6 | 50
mdSOFT3279 Act | mdSOFT3279 | Institutional | Bank | Implementation | Quantitative Analysis | None | Actual | 9 | 608 | 112 | 100 | 21 | 355 | 20 | 0
mdSOFT3279 Bud | mdSOFT3279 | Institutional | Bank | Implementation | Quantitative Analysis | None | Budget | 0 | 592 | 98 | 85 | 14 | 326 | 15 | 54
mdSOFT3280 Act | mdSOFT3280 | Institutional | Broker | Implementation | Quantitative Analysis | Inter-Market Analysis | Actual | 5 | 579 | 96 | 102 | 30 | 346 | 5 | 0
mdSOFT3280 Bud | mdSOFT3280 | Institutional | Broker | Implementation | Quantitative Analysis | Inter-Market Analysis | Budget | 0 | 576 | 86 | 82 | 20 | 329 | 6 | 53
mdSOFT3281 Act | mdSOFT3281 | Institutional | Bank | Implementation | Quantitative Analysis | None | Actual | 24 | 500 | 86 | 89 | 27 | 286 | 12 | 0
mdSOFT3281 Bud | mdSOFT3281 | Institutional | Bank | Implementation | Quantitative Analysis | None | Budget | 0 | 543 | 69 | 93 | 20 | 299 | 12 | 50
mdSOFT3282 Act | mdSOFT3282 | Institutional | Bank | Implementation | Quantitative Analysis | Technical Analysis | Actual | 22 | 423 | 65 | 65 | 20 | 262 | 11 | 0
mdSOFT3282 Bud | mdSOFT3282 | Institutional | Bank | Implementation | Quantitative Analysis | Technical Analysis | Budget | 0 | 500 | 73 | 71 | 17 | 282 | 11 | 46
mdSOFT3283 Act | mdSOFT3283 | Institutional | Retail | Implementation | Quantitative Analysis | Fundamental Analysis | Actual | 37 | 515 | 75 | 115 | 20 | 286 | 19 | 0
mdSOFT3283 Bud | mdSOFT3283 | Institutional | Retail | Implementation | Quantitative Analysis | Fundamental Analysis | Budget | 0 | 567 | 82 | 85 | 15 | 315 | 18 | 52
mdSOFT3284 Act | mdSOFT3284 | Institutional | Asset Manager | Implementation | Quantitative Analysis | Fundamental Analysis | Actual | 0 | 516 | 69 | 118 | 16 | 306 | 7 | 0
mdSOFT3284 Bud | mdSOFT3284 | Institutional | Asset Manager | Implementation | Quantitative Analysis | Fundamental Analysis | Budget | 0 | 560 | 79 | 104 | 16 | 305 | 5 | 51
mdSOFT3285 Act | mdSOFT3285 | Institutional | Bank | Implementation | Quantitative Analysis | Technical Analysis | Actual | 11 | 600 | 87 | 136 | 18 | 356 | 3 | 0
mdSOFT3285 Bud | mdSOFT3285 | Institutional | Bank | Implementation | Quantitative Analysis | Technical Analysis | Budget | 0 | 602 | 94 | 110 | 15 | 323 | 5 | 55
mdSOFT3286 Act | mdSOFT3286 | Institutional | Broker | Implementation | Quantitative Analysis | Technical Analysis | Actual | 11 | 397 | 71 | 97 | 13 | 197 | 19 | 0
mdSOFT3286 Bud | mdSOFT3286 | Institutional | Broker | Implementation | Quantitative Analysis | Technical Analysis | Budget | 0 | 422 | 64 | 70 | 13 | 219 | 17 | 39

## Original Data (2)
Code*Project ID*Client Group*Client Detail*Category*Main focus*Secondary focus*Report*Slippage in start date\Days: Total\Days: PM\Days: PSO\Days: BA\Days: Developer\Days: Tester\Days: Contingency | Code*Project | ID*Client | Group*Client | Detail*Category*Main | focus*Secondary | focus*Report*Slippage | in | start | date\Days: | Total\Days: | PM\Days: | PSO\Days: | BA\Days: | Developer\Days: | Tester\Days: | Contingency
mdSOFT3188 Act*mdSOFT3188*Retail*Retail*Wishlist*Technical Analysis*None*Actual*8\14\3\1\3\7\0\0 | mdSOFT3188 | Act*mdSOFT3188*Retail*Retail*Wishlist*Technical | Analysis*None*Actual*8\14\3\1\3\7\0\0
mdSOFT3233 Act*mdSOFT3233*Institutional*Retail*Enhancement*Fundamental Analysis*None*Actual*18\35\5\6\2\16\6\0 | mdSOFT3233 | Act*mdSOFT3233*Institutional*Retail*Enhancement*Fundamental | Analysis*None*Actual*18\35\5\6\2\16\6\0
mdSOFT3192 Bud*mdSOFT3192*Retail*Retail*Wishlist*Technical Analysis*None*Budget*0\23\3\1\2\14\3\0 | mdSOFT3192 | Bud*mdSOFT3192*Retail*Retail*Wishlist*Technical | Analysis*None*Budget*0\23\3\1\2\14\3\0
mdSOFT3204 Act*mdSOFT3204*Retail*Retail*Wishlist*Technical Analysis*None*Actual*3\21\3\2\2\11\3\0 | mdSOFT3204 | Act*mdSOFT3204*Retail*Retail*Wishlist*Technical | Analysis*None*Actual*3\21\3\2\2\11\3\0
mdSOFT3259 Bud*mdSOFT3259*Institutional*Bank*Implementation*Fundamental Analysis*Technical Analysis*Budget*0\374\51\65\10\198\16\34 | mdSOFT3259 | Bud*mdSOFT3259*Institutional*Bank*Implementation*Fundamental | Analysis*Technical | Analysis*Budget*0\374\51\65\10\198\16\34
mdSOFT3194 Act*mdSOFT3194*Retail*Retail*Wishlist*Technical Analysis*None*Actual*0\9\3\1\3\1\1\0 | mdSOFT3194 | Act*mdSOFT3194*Retail*Retail*Wishlist*Technical | Analysis*None*Actual*0\9\3\1\3\1\1\0
mdSOFT3277 Bud*mdSOFT3277*Institutional*Asset Manager*Implementation*Quantitative Analysis*Technical Analysis*Budget*0\473\73\81\14\252\10\43 | mdSOFT3277 | Bud*mdSOFT3277*Institutional*Asset | Manager*Implementation*Quantitative | Analysis*Technical | Analysis*Budget*0\473\73\81\14\252\10\43
mdSOFT3279 Bud*mdSOFT3279*Institutional*Bank*Implementation*Quantitative Analysis*None*Budget*0\592\98\85\14\326\15\54 | mdSOFT3279 | Bud*mdSOFT3279*Institutional*Bank*Implementation*Quantitative | Analysis*None*Budget*0\592\98\85\14\326\15\54
mdSOFT3282 Bud*mdSOFT3282*Institutional*Bank*Implementation*Quantitative Analysis*Technical Analysis*Budget*0\500\73\71\17\282\11\46 | mdSOFT3282 | Bud*mdSOFT3282*Institutional*Bank*Implementation*Quantitative | Analysis*Technical | Analysis*Budget*0\500\73\71\17\282\11\46
mdSOFT3286 Act*mdSOFT3286*Institutional*Broker*Implementation*Quantitative Analysis*Technical Analysis*Actual*11\397\71\97\13\197\19\0 | mdSOFT3286 | Act*mdSOFT3286*Institutional*Broker*Implementation*Quantitative | Analysis*Technical | Analysis*Actual*11\397\71\97\13\197\19\0
mdSOFT3232 Act*mdSOFT3232*Institutional*Asset Manager*Enhancement*Fundamental Analysis*None*Actual*13\27\3\5\6\8\5\0 | mdSOFT3232 | Act*mdSOFT3232*Institutional*Asset | Manager*Enhancement*Fundamental | Analysis*None*Actual*13\27\3\5\6\8\5\0
mdSOFT3266 Act*mdSOFT3266*Institutional*Hedge Fund*Implementation*Fundamental Analysis*Inter-Market Analysis*Actual*32\418\64\91\19\234\10\0 | mdSOFT3266 | Act*mdSOFT3266*Institutional*Hedge | Fund*Implementation*Fundamental | Analysis*Inter-Market | Analysis*Actual*32\418\64\91\19\234\10\0
mdSOFT3243 Act*mdSOFT3243*Institutional*Bank*Enhancement*Quantitative Analysis*None*Actual*5\16\4\1\4\3\4\0 | mdSOFT3243 | Act*mdSOFT3243*Institutional*Bank*Enhancement*Quantitative | Analysis*None*Actual*5\16\4\1\4\3\4\0
mdSOFT3283 Bud*mdSOFT3283*Institutional*Retail*Implementation*Quantitative Analysis*Fundamental Analysis*Budget*0\567\82\85\15\315\18\52 | mdSOFT3283 | Bud*mdSOFT3283*Institutional*Retail*Implementation*Quantitative | Analysis*Fundamental | Analysis*Budget*0\567\82\85\15\315\18\52
mdSOFT3227 Bud*mdSOFT3227*Retail*Retail*Wishlist*Quantitative Analysis*None*Budget*0\9\1\1\1\5\1\0 | mdSOFT3227 | Bud*mdSOFT3227*Retail*Retail*Wishlist*Quantitative | Analysis*None*Budget*0\9\1\1\1\5\1\0
mdSOFT3263 Bud*mdSOFT3263*Institutional*Bank*Implementation*Fundamental Analysis*None*Budget*0\633\77\111\19\348\20\58 | mdSOFT3263 | Bud*mdSOFT3263*Institutional*Bank*Implementation*Fundamental | Analysis*None*Budget*0\633\77\111\19\348\20\58
mdSOFT3239 Act*mdSOFT3239*Institutional*Retail*Enhancement*Inter-Market Analysis*None*Actual*7\21\1\2\2\15\1\0 | mdSOFT3239 | Act*mdSOFT3239*Institutional*Retail*Enhancement*Inter-Market | Analysis*None*Actual*7\21\1\2\2\15\1\0
mdSOFT3246 Act*mdSOFT3246*Institutional*Hedge Fund*Enhancement*Quantitative Analysis*None*Actual*18\24\5\4\1\11\3\0 | mdSOFT3246 | Act*mdSOFT3246*Institutional*Hedge | Fund*Enhancement*Quantitative | Analysis*None*Actual*18\24\5\4\1\11\3\0
mdSOFT3264 Bud*mdSOFT3264*Institutional*Retail*Implementation*Fundamental Analysis*Inter-Market Analysis*Budget*0\356\54\65\10\186\8\33 | mdSOFT3264 | Bud*mdSOFT3264*Institutional*Retail*Implementation*Fundamental | Analysis*Inter-Market | Analysis*Budget*0\356\54\65\10\186\8\33
mdSOFT3253 Act*mdSOFT3253*Institutional*Retail*Implementation*Technical Analysis*None*Actual*40\576\88\124\25\326\13\0 | mdSOFT3253 | Act*mdSOFT3253*Institutional*Retail*Implementation*Technical | Analysis*None*Actual*40\576\88\124\25\326\13\0
mdSOFT3258 Act*mdSOFT3258*Institutional*Hedge Fund*Implementation*Technical Analysis*Quantitative Analysis*Actual*23\518\79\88\24\312\15\0 | mdSOFT3258 | Act*mdSOFT3258*Institutional*Hedge | Fund*Implementation*Technical | Analysis*Quantitative | Analysis*Actual*23\518\79\88\24\312\15\0
mdSOFT3217 Bud*mdSOFT3217*Retail*Retail*Wishlist*Fundamental Analysis*None*Budget*0\17\2\2\2\9\2\0 | mdSOFT3217 | Bud*mdSOFT3217*Retail*Retail*Wishlist*Fundamental | Analysis*None*Budget*0\17\2\2\2\9\2\0
mdSOFT3249 Act*mdSOFT3249*Institutional*Hedge Fund*Enhancement*Quantitative Analysis*None*Actual*10\26\4\6\6\5\5\0 | mdSOFT3249 | Act*mdSOFT3249*Institutional*Hedge | Fund*Enhancement*Quantitative | Analysis*None*Actual*10\26\4\6\6\5\5\0
mdSOFT3227 Act*mdSOFT3227*Retail*Retail*Wishlist*Quantitative Analysis*None*Actual*2\10\1\2\1\6\0\0 | mdSOFT3227 | Act*mdSOFT3227*Retail*Retail*Wishlist*Quantitative | Analysis*None*Actual*2\10\1\2\1\6\0\0
mdSOFT3286 Bud*mdSOFT3286*Institutional*Broker*Implementation*Quantitative Analysis*Technical Analysis*Budget*0\422\64\70\13\219\17\39 | mdSOFT3286 | Bud*mdSOFT3286*Institutional*Broker*Implementation*Quantitative | Analysis*Technical | Analysis*Budget*0\422\64\70\13\219\17\39
mdSOFT3238 Bud*mdSOFT3238*Institutional*Bank*Enhancement*Fundamental Analysis*None*Budget*0\36\6\4\4\14\4\4 | mdSOFT3238 | Bud*mdSOFT3238*Institutional*Bank*Enhancement*Fundamental | Analysis*None*Budget*0\36\6\4\4\14\4\4
mdSOFT3196 Bud*mdSOFT3196*Retail*Retail*Wishlist*Technical Analysis*None*Budget*0\20\2\2\2\12\2\0 | mdSOFT3196 | Bud*mdSOFT3196*Retail*Retail*Wishlist*Technical | Analysis*None*Budget*0\20\2\2\2\12\2\0
mdSOFT3197 Act*mdSOFT3197*Retail*Retail*Wishlist*Technical Analysis*None*Actual*10\9\2\0\1\4\2\0 | mdSOFT3197 | Act*mdSOFT3197*Retail*Retail*Wishlist*Technical | Analysis*None*Actual*10\9\2\0\1\4\2\0
mdSOFT3278 Bud*mdSOFT3278*Institutional*Asset Manager*Implementation*Quantitative Analysis*None*Budget*0\546\79\82\13\316\6\50 | mdSOFT3278 | Bud*mdSOFT3278*Institutional*Asset | Manager*Implementation*Quantitative | Analysis*None*Budget*0\546\79\82\13\316\6\50
mdSOFT3245 Act*mdSOFT3245*Institutional*Hedge Fund*Enhancement*Quantitative Analysis*None*Actual*14\42\5\5\4\22\6\0 | mdSOFT3245 | Act*mdSOFT3245*Institutional*Hedge | Fund*Enhancement*Quantitative | Analysis*None*Actual*14\42\5\5\4\22\6\0
mdSOFT3208 Bud*mdSOFT3208*Retail*Retail*Wishlist*Fundamental Analysis*None*Budget*0\8\1\2\1\4\0\0 | mdSOFT3208 | Bud*mdSOFT3208*Retail*Retail*Wishlist*Fundamental | Analysis*None*Budget*0\8\1\2\1\4\0\0
mdSOFT3202 Act*mdSOFT3202*Retail*Retail*Wishlist*Technical Analysis*None*Actual*6\6\1\0\1\3\1\0 | mdSOFT3202 | Act*mdSOFT3202*Retail*Retail*Wishlist*Technical | Analysis*None*Actual*6\6\1\0\1\3\1\0
mdSOFT3267 Bud*mdSOFT3267*Institutional*Asset Manager*Implementation*Fundamental Analysis*Technical Analysis*Budget*0\388\54\54\19\206\19\36 | mdSOFT3267 | Bud*mdSOFT3267*Institutional*Asset | Manager*Implementation*Fundamental | Analysis*Technical | Analysis*Budget*0\388\54\54\19\206\19\36
mdSOFT3209 Act*mdSOFT3209*Retail*Retail*Wishlist*Fundamental Analysis*None*Actual*9\17\1\1\1\12\2\0 | mdSOFT3209 | Act*mdSOFT3209*Retail*Retail*Wishlist*Fundamental | Analysis*None*Actual*9\17\1\1\1\12\2\0
mdSOFT3216 Act*mdSOFT3216*Retail*Retail*Wishlist*Fundamental Analysis*None*Actual*2\6\1\0\3\1\1\0 | mdSOFT3216 | Act*mdSOFT3216*Retail*Retail*Wishlist*Fundamental | Analysis*None*Actual*2\6\1\0\3\1\1\0
mdSOFT3226 Bud*mdSOFT3226*Retail*Retail*Wishlist*Quantitative Analysis*None*Budget*0\24\3\2\2\15\2\0 | mdSOFT3226 | Bud*mdSOFT3226*Retail*Retail*Wishlist*Quantitative | Analysis*None*Budget*0\24\3\2\2\15\2\0
mdSOFT3211 Act*mdSOFT3211*Retail*Retail*Wishlist*Fundamental Analysis*None*Actual*8\16\1\2\1\9\3\0 | mdSOFT3211 | Act*mdSOFT3211*Retail*Retail*Wishlist*Fundamental | Analysis*None*Actual*8\16\1\2\1\9\3\0
mdSOFT3237 Act*mdSOFT3237*Institutional*Bank*Enhancement*Fundamental Analysis*None*Actual*8\40\6\4\3\20\7\0 | mdSOFT3237 | Act*mdSOFT3237*Institutional*Bank*Enhancement*Fundamental | Analysis*None*Actual*8\40\6\4\3\20\7\0
mdSOFT3193 Bud*mdSOFT3193*Retail*Retail*Wishlist*Technical Analysis*None*Budget*0\5\1\2\0\2\0\0 | mdSOFT3193 | Bud*mdSOFT3193*Retail*Retail*Wishlist*Technical | Analysis*None*Budget*0\5\1\2\0\2\0\0
mdSOFT3223 Act*mdSOFT3223*Retail*Retail*Wishlist*Inter-Market Analysis*None*Actual*10\9\1\0\3\5\0\0 | mdSOFT3223 | Act*mdSOFT3223*Retail*Retail*Wishlist*Inter-Market | Analysis*None*Actual*10\9\1\0\3\5\0\0
mdSOFT3238 Act*mdSOFT3238*Institutional*Bank*Enhancement*Fundamental Analysis*None*Actual*16\23\4\3\4\9\3\0 | mdSOFT3238 | Act*mdSOFT3238*Institutional*Bank*Enhancement*Fundamental | Analysis*None*Actual*16\23\4\3\4\9\3\0
mdSOFT3221 Act*mdSOFT3221*Retail*Retail*Wishlist*Inter-Market Analysis*None*Actual*3\17\4\0\1\11\1\0 | mdSOFT3221 | Act*mdSOFT3221*Retail*Retail*Wishlist*Inter-Market | Analysis*None*Actual*3\17\4\0\1\11\1\0
mdSOFT3284 Act*mdSOFT3284*Institutional*Asset Manager*Implementation*Quantitative Analysis*Fundamental Analysis*Actual*0\516\69\118\16\306\7\0 | mdSOFT3284 | Act*mdSOFT3284*Institutional*Asset | Manager*Implementation*Quantitative | Analysis*Fundamental | Analysis*Actual*0\516\69\118\16\306\7\0
mdSOFT3285 Bud*mdSOFT3285*Institutional*Bank*Implementation*Quantitative Analysis*Technical Analysis*Budget*0\602\94\110\15\323\5\55 | mdSOFT3285 | Bud*mdSOFT3285*Institutional*Bank*Implementation*Quantitative | Analysis*Technical | Analysis*Budget*0\602\94\110\15\323\5\55
mdSOFT3260 Act*mdSOFT3260*Institutional*Asset Manager*Implementation*Fundamental Analysis*None*Actual*38\412\75\86\20\224\7\0 | mdSOFT3260 | Act*mdSOFT3260*Institutional*Asset | Manager*Implementation*Fundamental | Analysis*None*Actual*38\412\75\86\20\224\7\0
mdSOFT3241 Bud*mdSOFT3241*Institutional*Hedge Fund*Enhancement*Inter-Market Analysis*None*Budget*0\35\5\3\5\14\4\4 | mdSOFT3241 | Bud*mdSOFT3241*Institutional*Hedge | Fund*Enhancement*Inter-Market | Analysis*None*Budget*0\35\5\3\5\14\4\4
mdSOFT3216 Bud*mdSOFT3216*Retail*Retail*Wishlist*Fundamental Analysis*None*Budget*0\11\1\1\2\5\2\0 | mdSOFT3216 | Bud*mdSOFT3216*Retail*Retail*Wishlist*Fundamental | Analysis*None*Budget*0\11\1\1\2\5\2\0
mdSOFT3193 Act*mdSOFT3193*Retail*Retail*Wishlist*Technical Analysis*None*Actual*6\7\1\2\1\3\0\0 | mdSOFT3193 | Act*mdSOFT3193*Retail*Retail*Wishlist*Technical | Analysis*None*Actual*6\7\1\2\1\3\0\0
mdSOFT3278 Act*mdSOFT3278*Institutional*Asset Manager*Implementation*Quantitative Analysis*None*Actual*35\539\76\95\9\353\6\0 | mdSOFT3278 | Act*mdSOFT3278*Institutional*Asset | Manager*Implementation*Quantitative | Analysis*None*Actual*35\539\76\95\9\353\6\0
mdSOFT3214 Act*mdSOFT3214*Retail*Retail*Wishlist*Fundamental Analysis*None*Actual*0\12\1\2\4\5\0\0 | mdSOFT3214 | Act*mdSOFT3214*Retail*Retail*Wishlist*Fundamental | Analysis*None*Actual*0\12\1\2\4\5\0\0
mdSOFT3262 Bud*mdSOFT3262*Institutional*Asset Manager*Implementation*Fundamental Analysis*None*Budget*0\352\55\53\12\191\9\32 | mdSOFT3262 | Bud*mdSOFT3262*Institutional*Asset | Manager*Implementation*Fundamental | Analysis*None*Budget*0\352\55\53\12\191\9\32
mdSOFT3274 Act*mdSOFT3274*Institutional*Broker*Implementation*Quantitative Analysis*Fundamental Analysis*Actual*10\541\87\104\13\324\13\0 | mdSOFT3274 | Act*mdSOFT3274*Institutional*Broker*Implementation*Quantitative | Analysis*Fundamental | Analysis*Actual*10\541\87\104\13\324\13\0
mdSOFT3250 Bud*mdSOFT3250*Institutional*Hedge Fund*Enhancement*Quantitative Analysis*None*Budget*0\42\6\5\3\20\4\4 | mdSOFT3250 | Bud*mdSOFT3250*Institutional*Hedge | Fund*Enhancement*Quantitative | Analysis*None*Budget*0\42\6\5\3\20\4\4
mdSOFT3187 Bud*mdSOFT3187*Retail*Retail*Wishlist*Technical Analysis*None*Budget*0\24\3\2\3\15\1\0 | mdSOFT3187 | Bud*mdSOFT3187*Retail*Retail*Wishlist*Technical | Analysis*None*Budget*0\24\3\2\3\15\1\0
mdSOFT3231 Act*mdSOFT3231*Institutional*Broker*Enhancement*Fundamental Analysis*None*Actual*8\11\2\1\3\4\1\0 | mdSOFT3231 | Act*mdSOFT3231*Institutional*Broker*Enhancement*Fundamental | Analysis*None*Actual*8\11\2\1\3\4\1\0
mdSOFT3280 Act*mdSOFT3280*Institutional*Broker*Implementation*Quantitative Analysis*Inter-Market Analysis*Actual*5\579\96\102\30\346\5\0 | mdSOFT3280 | Act*mdSOFT3280*Institutional*Broker*Implementation*Quantitative | Analysis*Inter-Market | Analysis*Actual*5\579\96\102\30\346\5\0
mdSOFT3190 Bud*mdSOFT3190*Retail*Retail*Wishlist*Technical Analysis*None*Budget*0\11\1\1\1\6\2\0 | mdSOFT3190 | Bud*mdSOFT3190*Retail*Retail*Wishlist*Technical | Analysis*None*Budget*0\11\1\1\1\6\2\0
mdSOFT3191 Bud*mdSOFT3191*Retail*Retail*Wishlist*Technical Analysis*None*Budget*0\13\1\2\2\7\1\0 | mdSOFT3191 | Bud*mdSOFT3191*Retail*Retail*Wishlist*Technical | Analysis*None*Budget*0\13\1\2\2\7\1\0
mdSOFT3210 Bud*mdSOFT3210*Retail*Retail*Wishlist*Fundamental Analysis*None*Budget*0\22\3\2\1\14\2\0 | mdSOFT3210 | Bud*mdSOFT3210*Retail*Retail*Wishlist*Fundamental | Analysis*None*Budget*0\22\3\2\1\14\2\0
mdSOFT3249 Bud*mdSOFT3249*Institutional*Hedge Fund*Enhancement*Quantitative Analysis*None*Budget*0\38\5\6\4\15\4\4 | mdSOFT3249 | Bud*mdSOFT3249*Institutional*Hedge | Fund*Enhancement*Quantitative | Analysis*None*Budget*0\38\5\6\4\15\4\4
mdSOFT3233 Bud*mdSOFT3233*Institutional*Retail*Enhancement*Fundamental Analysis*None*Budget*0\44\7\6\4\18\5\4 | mdSOFT3233 | Bud*mdSOFT3233*Institutional*Retail*Enhancement*Fundamental | Analysis*None*Budget*0\44\7\6\4\18\5\4
mdSOFT3205 Bud*mdSOFT3205*Retail*Retail*Wishlist*Technical Analysis*None*Budget*0\11\1\1\2\6\1\0 | mdSOFT3205 | Bud*mdSOFT3205*Retail*Retail*Wishlist*Technical | Analysis*None*Budget*0\11\1\1\2\6\1\0
mdSOFT3250 Act*mdSOFT3250*Institutional*Hedge Fund*Enhancement*Quantitative Analysis*None*Actual*3\41\6\4\5\20\6\0 | mdSOFT3250 | Act*mdSOFT3250*Institutional*Hedge | Fund*Enhancement*Quantitative | Analysis*None*Actual*3\41\6\4\5\20\6\0
mdSOFT3270 Act*mdSOFT3270*Institutional*Bank*Implementation*Inter-Market Analysis*Quantitative Analysis*Actual*3\543\109\80\17\332\5\0 | mdSOFT3270 | Act*mdSOFT3270*Institutional*Bank*Implementation*Inter-Market | Analysis*Quantitative | Analysis*Actual*3\543\109\80\17\332\5\0
mdSOFT3275 Bud*mdSOFT3275*Institutional*Asset Manager*Implementation*Quantitative Analysis*Fundamental Analysis*Budget*0\321\42\57\14\163\15\30 | mdSOFT3275 | Bud*mdSOFT3275*Institutional*Asset | Manager*Implementation*Quantitative | Analysis*Fundamental | Analysis*Budget*0\321\42\57\14\163\15\30
mdSOFT3252 Bud*mdSOFT3252*Institutional*Bank*Implementation*Technical Analysis*None*Budget*0\362\40\67\17\191\14\33 | mdSOFT3252 | Bud*mdSOFT3252*Institutional*Bank*Implementation*Technical | Analysis*None*Budget*0\362\40\67\17\191\14\33
mdSOFT3254 Act*mdSOFT3254*Institutional*Asset Manager*Implementation*Technical Analysis*None*Actual*17\366\64\90\12\194\6\0 | mdSOFT3254 | Act*mdSOFT3254*Institutional*Asset | Manager*Implementation*Technical | Analysis*None*Actual*17\366\64\90\12\194\6\0
mdSOFT3229 Act*mdSOFT3229*Institutional*Bank*Enhancement*Technical Analysis*None*Actual*7\25\4\4\2\11\4\0 | mdSOFT3229 | Act*mdSOFT3229*Institutional*Bank*Enhancement*Technical | Analysis*None*Actual*7\25\4\4\2\11\4\0
mdSOFT3224 Act*mdSOFT3224*Retail*Retail*Wishlist*Inter-Market Analysis*None*Actual*7\16\1\3\2\8\2\0 | mdSOFT3224 | Act*mdSOFT3224*Retail*Retail*Wishlist*Inter-Market | Analysis*None*Actual*7\16\1\3\2\8\2\0
mdSOFT3270 Bud*mdSOFT3270*Institutional*Bank*Implementation*Inter-Market Analysis*Quantitative Analysis*Budget*0\599\92\88\18\339\7\55 | mdSOFT3270 | Bud*mdSOFT3270*Institutional*Bank*Implementation*Inter-Market | Analysis*Quantitative | Analysis*Budget*0\599\92\88\18\339\7\55
mdSOFT3218 Bud*mdSOFT3218*Retail*Retail*Wishlist*Fundamental Analysis*None*Budget*0\19\2\1\2\11\3\0 | mdSOFT3218 | Bud*mdSOFT3218*Retail*Retail*Wishlist*Fundamental | Analysis*None*Budget*0\19\2\1\2\11\3\0
mdSOFT3252 Act*mdSOFT3252*Institutional*Bank*Implementation*Technical Analysis*None*Actual*28\398\35\81\27\238\17\0 | mdSOFT3252 | Act*mdSOFT3252*Institutional*Bank*Implementation*Technical | Analysis*None*Actual*28\398\35\81\27\238\17\0
mdSOFT3188 Bud*mdSOFT3188*Retail*Retail*Wishlist*Technical Analysis*None*Budget*0\8\1\1\3\3\0\0 | mdSOFT3188 | Bud*mdSOFT3188*Retail*Retail*Wishlist*Technical | Analysis*None*Budget*0\8\1\1\3\3\0\0
mdSOFT3251 Bud*mdSOFT3251*Institutional*Asset Manager*Enhancement*Quantitative Analysis*None*Budget*0\27\4\4\3\10\3\3 | mdSOFT3251 | Bud*mdSOFT3251*Institutional*Asset | Manager*Enhancement*Quantitative | Analysis*None*Budget*0\27\4\4\3\10\3\3
mdSOFT3218 Act*mdSOFT3218*Retail*Retail*Wishlist*Fundamental Analysis*None*Actual*4\26\4\0\3\15\4\0 | mdSOFT3218 | Act*mdSOFT3218*Retail*Retail*Wishlist*Fundamental | Analysis*None*Actual*4\26\4\0\3\15\4\0
mdSOFT3228 Act*mdSOFT3228*Institutional*Retail*Enhancement*Technical Analysis*None*Actual*3\16\1\1\4\9\1\0 | mdSOFT3228 | Act*mdSOFT3228*Institutional*Retail*Enhancement*Technical | Analysis*None*Actual*3\16\1\1\4\9\1\0
mdSOFT3215 Bud*mdSOFT3215*Retail*Retail*Wishlist*Fundamental Analysis*None*Budget*0\12\1\2\2\5\2\0 | mdSOFT3215 | Bud*mdSOFT3215*Retail*Retail*Wishlist*Fundamental | Analysis*None*Budget*0\12\1\2\2\5\2\0
mdSOFT3276 Act*mdSOFT3276*Institutional*Bank*Implementation*Quantitative Analysis*Fundamental Analysis*Actual*5\451\86\84\11\266\4\0 | mdSOFT3276 | Act*mdSOFT3276*Institutional*Bank*Implementation*Quantitative | Analysis*Fundamental | Analysis*Actual*5\451\86\84\11\266\4\0
mdSOFT3255 Act*mdSOFT3255*Institutional*Bank*Implementation*Technical Analysis*Inter-Market Analysis*Actual*20\501\86\87\16\299\13\0 | mdSOFT3255 | Act*mdSOFT3255*Institutional*Bank*Implementation*Technical | Analysis*Inter-Market | Analysis*Actual*20\501\86\87\16\299\13\0
mdSOFT3194 Bud*mdSOFT3194*Retail*Retail*Wishlist*Technical Analysis*None*Budget*0\10\1\2\3\4\0\0 | mdSOFT3194 | Bud*mdSOFT3194*Retail*Retail*Wishlist*Technical | Analysis*None*Budget*0\10\1\2\3\4\0\0
mdSOFT3208 Act*mdSOFT3208*Retail*Retail*Wishlist*Fundamental Analysis*None*Actual*7\7\1\2\1\2\1\0 | mdSOFT3208 | Act*mdSOFT3208*Retail*Retail*Wishlist*Fundamental | Analysis*None*Actual*7\7\1\2\1\2\1\0
mdSOFT3243 Bud*mdSOFT3243*Institutional*Bank*Enhancement*Quantitative Analysis*None*Budget*0\17\3\2\2\6\2\2 | mdSOFT3243 | Bud*mdSOFT3243*Institutional*Bank*Enhancement*Quantitative | Analysis*None*Budget*0\17\3\2\2\6\2\2
mdSOFT3214 Bud*mdSOFT3214*Retail*Retail*Wishlist*Fundamental Analysis*None*Budget*0\9\1\2\3\3\0\0 | mdSOFT3214 | Bud*mdSOFT3214*Retail*Retail*Wishlist*Fundamental | Analysis*None*Budget*0\9\1\2\3\3\0\0
mdSOFT3201 Bud*mdSOFT3201*Retail*Retail*Wishlist*Technical Analysis*None*Budget*0\20\2\1\3\12\2\0 | mdSOFT3201 | Bud*mdSOFT3201*Retail*Retail*Wishlist*Technical | Analysis*None*Budget*0\20\2\1\3\12\2\0
mdSOFT3285 Act*mdSOFT3285*Institutional*Bank*Implementation*Quantitative Analysis*Technical Analysis*Actual*11\600\87\136\18\356\3\0 | mdSOFT3285 | Act*mdSOFT3285*Institutional*Bank*Implementation*Quantitative | Analysis*Technical | Analysis*Actual*11\600\87\136\18\356\3\0
mdSOFT3234 Act*mdSOFT3234*Institutional*Hedge Fund*Enhancement*Fundamental Analysis*None*Actual*3\22\5\3\3\7\4\0 | mdSOFT3234 | Act*mdSOFT3234*Institutional*Hedge | Fund*Enhancement*Fundamental | Analysis*None*Actual*3\22\5\3\3\7\4\0
mdSOFT3237 Bud*mdSOFT3237*Institutional*Bank*Enhancement*Fundamental Analysis*None*Budget*0\44\6\6\5\18\5\4 | mdSOFT3237 | Bud*mdSOFT3237*Institutional*Bank*Enhancement*Fundamental | Analysis*None*Budget*0\44\6\6\5\18\5\4
mdSOFT3203 Act*mdSOFT3203*Retail*Retail*Wishlist*Technical Analysis*None*Actual*2\14\1\2\0\11\0\0 | mdSOFT3203 | Act*mdSOFT3203*Retail*Retail*Wishlist*Technical | Analysis*None*Actual*2\14\1\2\0\11\0\0
mdSOFT3190 Act*mdSOFT3190*Retail*Retail*Wishlist*Technical Analysis*None*Actual*7\15\3\2\2\6\2\0 | mdSOFT3190 | Act*mdSOFT3190*Retail*Retail*Wishlist*Technical | Analysis*None*Actual*7\15\3\2\2\6\2\0
mdSOFT3283 Act*mdSOFT3283*Institutional*Retail*Implementation*Quantitative Analysis*Fundamental Analysis*Actual*37\515\75\115\20\286\19\0 | mdSOFT3283 | Act*mdSOFT3283*Institutional*Retail*Implementation*Quantitative | Analysis*Fundamental | Analysis*Actual*37\515\75\115\20\286\19\0
mdSOFT3265 Act*mdSOFT3265*Institutional*Bank*Implementation*Fundamental Analysis*None*Actual*1\393\51\59\21\250\12\0 | mdSOFT3265 | Act*mdSOFT3265*Institutional*Bank*Implementation*Fundamental | Analysis*None*Actual*1\393\51\59\21\250\12\0
mdSOFT3247 Bud*mdSOFT3247*Institutional*Bank*Enhancement*Quantitative Analysis*None*Budget*0\31\4\4\5\12\3\3 | mdSOFT3247 | Bud*mdSOFT3247*Institutional*Bank*Enhancement*Quantitative | Analysis*None*Budget*0\31\4\4\5\12\3\3
mdSOFT3242 Bud*mdSOFT3242*Institutional*Broker*Enhancement*Inter-Market Analysis*None*Budget*0\49\8\6\5\21\4\5 | mdSOFT3242 | Bud*mdSOFT3242*Institutional*Broker*Enhancement*Inter-Market | Analysis*None*Budget*0\49\8\6\5\21\4\5
mdSOFT3271 Bud*mdSOFT3271*Institutional*Retail*Implementation*Inter-Market Analysis*Quantitative Analysis*Budget*0\625\100\106\16\332\14\57 | mdSOFT3271 | Bud*mdSOFT3271*Institutional*Retail*Implementation*Inter-Market | Analysis*Quantitative | Analysis*Budget*0\625\100\106\16\332\14\57
mdSOFT3254 Bud*mdSOFT3254*Institutional*Asset Manager*Implementation*Technical Analysis*None*Budget*0\402\60\73\16\208\8\37 | mdSOFT3254 | Bud*mdSOFT3254*Institutional*Asset | Manager*Implementation*Technical | Analysis*None*Budget*0\402\60\73\16\208\8\37
mdSOFT3241 Act*mdSOFT3241*Institutional*Hedge Fund*Enhancement*Inter-Market Analysis*None*Actual*11\35\7\4\3\18\3\0 | mdSOFT3241 | Act*mdSOFT3241*Institutional*Hedge | Fund*Enhancement*Inter-Market | Analysis*None*Actual*11\35\7\4\3\18\3\0
mdSOFT3277 Act*mdSOFT3277*Institutional*Asset Manager*Implementation*Quantitative Analysis*Technical Analysis*Actual*17\424\65\78\22\250\9\0 | mdSOFT3277 | Act*mdSOFT3277*Institutional*Asset | Manager*Implementation*Quantitative | Analysis*Technical | Analysis*Actual*17\424\65\78\22\250\9\0
mdSOFT3273 Act*mdSOFT3273*Institutional*Retail*Implementation*Inter-Market Analysis*Fundamental Analysis*Actual*18\455\56\83\23\272\21\0 | mdSOFT3273 | Act*mdSOFT3273*Institutional*Retail*Implementation*Inter-Market | Analysis*Fundamental | Analysis*Actual*18\455\56\83\23\272\21\0
mdSOFT3219 Act*mdSOFT3219*Retail*Retail*Wishlist*Fundamental Analysis*None*Actual*6\14\2\0\3\9\0\0 | mdSOFT3219 | Act*mdSOFT3219*Retail*Retail*Wishlist*Fundamental | Analysis*None*Actual*6\14\2\0\3\9\0\0
mdSOFT3204 Bud*mdSOFT3204*Retail*Retail*Wishlist*Technical Analysis*None*Budget*0\17\2\2\1\10\2\0 | mdSOFT3204 | Bud*mdSOFT3204*Retail*Retail*Wishlist*Technical | Analysis*None*Budget*0\17\2\2\1\10\2\0
mdSOFT3276 Bud*mdSOFT3276*Institutional*Bank*Implementation*Quantitative Analysis*Fundamental Analysis*Budget*0\494\73\76\13\282\5\45 | mdSOFT3276 | Bud*mdSOFT3276*Institutional*Bank*Implementation*Quantitative | Analysis*Fundamental | Analysis*Budget*0\494\73\76\13\282\5\45
mdSOFT3248 Bud*mdSOFT3248*Institutional*Asset Manager*Enhancement*Quantitative Analysis*None*Budget*0\39\5\6\4\16\4\4 | mdSOFT3248 | Bud*mdSOFT3248*Institutional*Asset | Manager*Enhancement*Quantitative | Analysis*None*Budget*0\39\5\6\4\16\4\4
mdSOFT3215 Act*mdSOFT3215*Retail*Retail*Wishlist*Fundamental Analysis*None*Actual*3\16\1\1\1\10\3\0 | mdSOFT3215 | Act*mdSOFT3215*Retail*Retail*Wishlist*Fundamental | Analysis*None*Actual*3\16\1\1\1\10\3\0
mdSOFT3268 Bud*mdSOFT3268*Institutional*Broker*Implementation*Inter-Market Analysis*Technical Analysis*Budget*0\363\53\51\20\189\17\33 | mdSOFT3268 | Bud*mdSOFT3268*Institutional*Broker*Implementation*Inter-Market | Analysis*Technical | Analysis*Budget*0\363\53\51\20\189\17\33
mdSOFT3240 Act*mdSOFT3240*Institutional*Bank*Enhancement*Inter-Market Analysis*None*Actual*9\10\1\2\1\3\3\0 | mdSOFT3240 | Act*mdSOFT3240*Institutional*Bank*Enhancement*Inter-Market | Analysis*None*Actual*9\10\1\2\1\3\3\0
mdSOFT3246 Bud*mdSOFT3246*Institutional*Hedge Fund*Enhancement*Quantitative Analysis*None*Budget*0\18\3\2\1\8\2\2 | mdSOFT3246 | Bud*mdSOFT3246*Institutional*Hedge | Fund*Enhancement*Quantitative | Analysis*None*Budget*0\18\3\2\1\8\2\2
mdSOFT3230 Act*mdSOFT3230*Institutional*Asset Manager*Enhancement*Technical Analysis*None*Actual*2\28\6\6\2\9\5\0 | mdSOFT3230 | Act*mdSOFT3230*Institutional*Asset | Manager*Enhancement*Technical | Analysis*None*Actual*2\28\6\6\2\9\5\0
mdSOFT3272 Bud*mdSOFT3272*Institutional*Asset Manager*Implementation*Inter-Market Analysis*None*Budget*0\329\39\46\13\185\16\30 | mdSOFT3272 | Bud*mdSOFT3272*Institutional*Asset | Manager*Implementation*Inter-Market | Analysis*None*Budget*0\329\39\46\13\185\16\30
mdSOFT3229 Bud*mdSOFT3229*Institutional*Bank*Enhancement*Technical Analysis*None*Budget*0\17\3\2\1\7\2\2 | mdSOFT3229 | Bud*mdSOFT3229*Institutional*Bank*Enhancement*Technical | Analysis*None*Budget*0\17\3\2\1\7\2\2
mdSOFT3245 Bud*mdSOFT3245*Institutional*Hedge Fund*Enhancement*Quantitative Analysis*None*Budget*0\38\5\5\3\16\5\4 | mdSOFT3245 | Bud*mdSOFT3245*Institutional*Hedge | Fund*Enhancement*Quantitative | Analysis*None*Budget*0\38\5\5\3\16\5\4
mdSOFT3256 Act*mdSOFT3256*Institutional*Asset Manager*Implementation*Technical Analysis*None*Actual*33\352\56\42\15\227\12\0 | mdSOFT3256 | Act*mdSOFT3256*Institutional*Asset | Manager*Implementation*Technical | Analysis*None*Actual*33\352\56\42\15\227\12\0
mdSOFT3282 Act*mdSOFT3282*Institutional*Bank*Implementation*Quantitative Analysis*Technical Analysis*Actual*22\423\65\65\20\262\11\0 | mdSOFT3282 | Act*mdSOFT3282*Institutional*Bank*Implementation*Quantitative | Analysis*Technical | Analysis*Actual*22\423\65\65\20\262\11\0
mdSOFT3263 Act*mdSOFT3263*Institutional*Bank*Implementation*Fundamental Analysis*None*Actual*11\591\81\135\14\337\24\0 | mdSOFT3263 | Act*mdSOFT3263*Institutional*Bank*Implementation*Fundamental | Analysis*None*Actual*11\591\81\135\14\337\24\0
mdSOFT3272 Act*mdSOFT3272*Institutional*Asset Manager*Implementation*Inter-Market Analysis*None*Actual*22\368\36\57\23\231\21\0 | mdSOFT3272 | Act*mdSOFT3272*Institutional*Asset | Manager*Implementation*Inter-Market | Analysis*None*Actual*22\368\36\57\23\231\21\0
mdSOFT3236 Bud*mdSOFT3236*Institutional*Hedge Fund*Enhancement*Fundamental Analysis*None*Budget*0\15\2\2\2\5\2\2 | mdSOFT3236 | Bud*mdSOFT3236*Institutional*Hedge | Fund*Enhancement*Fundamental | Analysis*None*Budget*0\15\2\2\2\5\2\2
mdSOFT3244 Act*mdSOFT3244*Institutional*Asset Manager*Enhancement*Quantitative Analysis*None*Actual*15\21\3\4\3\8\3\0 | mdSOFT3244 | Act*mdSOFT3244*Institutional*Asset | Manager*Enhancement*Quantitative | Analysis*None*Actual*15\21\3\4\3\8\3\0
mdSOFT3239 Bud*mdSOFT3239*Institutional*Retail*Enhancement*Inter-Market Analysis*None*Budget*0\13\2\2\1\5\1\2 | mdSOFT3239 | Bud*mdSOFT3239*Institutional*Retail*Enhancement*Inter-Market | Analysis*None*Budget*0\13\2\2\1\5\1\2
mdSOFT3200 Act*mdSOFT3200*Retail*Retail*Wishlist*Technical Analysis*None*Actual*8\28\4\2\4\15\3\0 | mdSOFT3200 | Act*mdSOFT3200*Retail*Retail*Wishlist*Technical | Analysis*None*Actual*8\28\4\2\4\15\3\0
mdSOFT3267 Act*mdSOFT3267*Institutional*Asset Manager*Implementation*Fundamental Analysis*Technical Analysis*Actual*17\389\47\65\21\236\20\0 | mdSOFT3267 | Act*mdSOFT3267*Institutional*Asset | Manager*Implementation*Fundamental | Analysis*Technical | Analysis*Actual*17\389\47\65\21\236\20\0
mdSOFT3255 Bud*mdSOFT3255*Institutional*Bank*Implementation*Technical Analysis*Inter-Market Analysis*Budget*0\555\92\83\12\307\10\51 | mdSOFT3255 | Bud*mdSOFT3255*Institutional*Bank*Implementation*Technical | Analysis*Inter-Market | Analysis*Budget*0\555\92\83\12\307\10\51
mdSOFT3260 Bud*mdSOFT3260*Institutional*Asset Manager*Implementation*Fundamental Analysis*None*Budget*0\442\55\78\12\251\5\41 | mdSOFT3260 | Bud*mdSOFT3260*Institutional*Asset | Manager*Implementation*Fundamental | Analysis*None*Budget*0\442\55\78\12\251\5\41
mdSOFT3217 Act*mdSOFT3217*Retail*Retail*Wishlist*Fundamental Analysis*None*Actual*7\9\1\1\2\4\1\0 | mdSOFT3217 | Act*mdSOFT3217*Retail*Retail*Wishlist*Fundamental | Analysis*None*Actual*7\9\1\1\2\4\1\0
mdSOFT3257 Bud*mdSOFT3257*Institutional*Broker*Implementation*Technical Analysis*None*Budget*0\361\55\59\10\197\7\33 | mdSOFT3257 | Bud*mdSOFT3257*Institutional*Broker*Implementation*Technical | Analysis*None*Budget*0\361\55\59\10\197\7\33
mdSOFT3258 Bud*mdSOFT3258*Institutional*Hedge Fund*Implementation*Technical Analysis*Quantitative Analysis*Budget*0\469\66\68\17\263\12\43 | mdSOFT3258 | Bud*mdSOFT3258*Institutional*Hedge | Fund*Implementation*Technical | Analysis*Quantitative | Analysis*Budget*0\469\66\68\17\263\12\43
mdSOFT3225 Act*mdSOFT3225*Retail*Retail*Wishlist*Inter-Market Analysis*None*Actual*1\23\1\1\3\16\2\0 | mdSOFT3225 | Act*mdSOFT3225*Retail*Retail*Wishlist*Inter-Market | Analysis*None*Actual*1\23\1\1\3\16\2\0
mdSOFT3234 Bud*mdSOFT3234*Institutional*Hedge Fund*Enhancement*Fundamental Analysis*None*Budget*0\16\2\1\2\7\2\2 | mdSOFT3234 | Bud*mdSOFT3234*Institutional*Hedge | Fund*Enhancement*Fundamental | Analysis*None*Budget*0\16\2\1\2\7\2\2
mdSOFT3202 Bud*mdSOFT3202*Retail*Retail*Wishlist*Technical Analysis*None*Budget*0\12\1\1\2\6\2\0 | mdSOFT3202 | Bud*mdSOFT3202*Retail*Retail*Wishlist*Technical | Analysis*None*Budget*0\12\1\1\2\6\2\0
mdSOFT3273 Bud*mdSOFT3273*Institutional*Retail*Implementation*Inter-Market Analysis*Fundamental Analysis*Budget*0\468\53\69\17\266\20\43 | mdSOFT3273 | Bud*mdSOFT3273*Institutional*Retail*Implementation*Inter-Market | Analysis*Fundamental | Analysis*Budget*0\468\53\69\17\266\20\43
mdSOFT3212 Bud*mdSOFT3212*Retail*Retail*Wishlist*Fundamental Analysis*None*Budget*0\13\1\2\2\7\1\0 | mdSOFT3212 | Bud*mdSOFT3212*Retail*Retail*Wishlist*Fundamental | Analysis*None*Budget*0\13\1\2\2\7\1\0
mdSOFT3269 Act*mdSOFT3269*Institutional*Bank*Implementation*Inter-Market Analysis*Fundamental Analysis*Actual*23\567\106\94\16\331\20\0 | mdSOFT3269 | Act*mdSOFT3269*Institutional*Bank*Implementation*Inter-Market | Analysis*Fundamental | Analysis*Actual*23\567\106\94\16\331\20\0
mdSOFT3219 Bud*mdSOFT3219*Retail*Retail*Wishlist*Fundamental Analysis*None*Budget*0\8\1\1\2\4\0\0 | mdSOFT3219 | Bud*mdSOFT3219*Retail*Retail*Wishlist*Fundamental | Analysis*None*Budget*0\8\1\1\2\4\0\0
mdSOFT3213 Act*mdSOFT3213*Retail*Retail*Wishlist*Fundamental Analysis*None*Actual*4\21\4\1\2\13\1\0 | mdSOFT3213 | Act*mdSOFT3213*Retail*Retail*Wishlist*Fundamental | Analysis*None*Actual*4\21\4\1\2\13\1\0
mdSOFT3206 Act*mdSOFT3206*Retail*Retail*Wishlist*Technical Analysis*None*Actual*0\3\1\0\0\2\0\0 | mdSOFT3206 | Act*mdSOFT3206*Retail*Retail*Wishlist*Technical | Analysis*None*Actual*0\3\1\0\0\2\0\0
mdSOFT3189 Bud*mdSOFT3189*Retail*Retail*Wishlist*Technical Analysis*None*Budget*0\24\3\2\1\15\3\0 | mdSOFT3189 | Bud*mdSOFT3189*Retail*Retail*Wishlist*Technical | Analysis*None*Budget*0\24\3\2\1\15\3\0
mdSOFT3231 Bud*mdSOFT3231*Institutional*Broker*Enhancement*Fundamental Analysis*None*Budget*0\18\3\2\1\8\2\2 | mdSOFT3231 | Bud*mdSOFT3231*Institutional*Broker*Enhancement*Fundamental | Analysis*None*Budget*0\18\3\2\1\8\2\2
mdSOFT3207 Bud*mdSOFT3207*Retail*Retail*Wishlist*Technical Analysis*None*Budget*0\7\1\1\2\3\0\0 | mdSOFT3207 | Bud*mdSOFT3207*Retail*Retail*Wishlist*Technical | Analysis*None*Budget*0\7\1\1\2\3\0\0
mdSOFT3197 Bud*mdSOFT3197*Retail*Retail*Wishlist*Technical Analysis*None*Budget*0\13\2\1\1\8\1\0 | mdSOFT3197 | Bud*mdSOFT3197*Retail*Retail*Wishlist*Technical | Analysis*None*Budget*0\13\2\1\1\8\1\0
mdSOFT3226 Act*mdSOFT3226*Retail*Retail*Wishlist*Quantitative Analysis*None*Actual*4\23\5\1\2\13\2\0 | mdSOFT3226 | Act*mdSOFT3226*Retail*Retail*Wishlist*Quantitative | Analysis*None*Actual*4\23\5\1\2\13\2\0
mdSOFT3187 Act*mdSOFT3187*Retail*Retail*Wishlist*Technical Analysis*None*Actual*3\21\3\2\3\12\1\0 | mdSOFT3187 | Act*mdSOFT3187*Retail*Retail*Wishlist*Technical | Analysis*None*Actual*3\21\3\2\3\12\1\0
mdSOFT3225 Bud*mdSOFT3225*Retail*Retail*Wishlist*Inter-Market Analysis*None*Budget*0\20\2\1\3\12\2\0 | mdSOFT3225 | Bud*mdSOFT3225*Retail*Retail*Wishlist*Inter-Market | Analysis*None*Budget*0\20\2\1\3\12\2\0
mdSOFT3199 Act*mdSOFT3199*Retail*Retail*Wishlist*Technical Analysis*None*Actual*4\18\1\2\1\13\1\0 | mdSOFT3199 | Act*mdSOFT3199*Retail*Retail*Wishlist*Technical | Analysis*None*Actual*4\18\1\2\1\13\1\0
mdSOFT3240 Bud*mdSOFT3240*Institutional*Bank*Enhancement*Inter-Market Analysis*None*Budget*0\14\2\1\2\5\2\2 | mdSOFT3240 | Bud*mdSOFT3240*Institutional*Bank*Enhancement*Inter-Market | Analysis*None*Budget*0\14\2\1\2\5\2\2
mdSOFT3209 Bud*mdSOFT3209*Retail*Retail*Wishlist*Fundamental Analysis*None*Budget*0\18\2\2\2\11\1\0 | mdSOFT3209 | Bud*mdSOFT3209*Retail*Retail*Wishlist*Fundamental | Analysis*None*Budget*0\18\2\2\2\11\1\0
mdSOFT3235 Act*mdSOFT3235*Institutional*Bank*Enhancement*Fundamental Analysis*None*Actual*10\16\3\1\1\8\3\0 | mdSOFT3235 | Act*mdSOFT3235*Institutional*Bank*Enhancement*Fundamental | Analysis*None*Actual*10\16\3\1\1\8\3\0
mdSOFT3228 Bud*mdSOFT3228*Institutional*Retail*Enhancement*Technical Analysis*None*Budget*0\17\3\1\2\7\2\2 | mdSOFT3228 | Bud*mdSOFT3228*Institutional*Retail*Enhancement*Technical | Analysis*None*Budget*0\17\3\1\2\7\2\2
mdSOFT3224 Bud*mdSOFT3224*Retail*Retail*Wishlist*Inter-Market Analysis*None*Budget*0\12\1\2\1\7\1\0 | mdSOFT3224 | Bud*mdSOFT3224*Retail*Retail*Wishlist*Inter-Market | Analysis*None*Budget*0\12\1\2\1\7\1\0
mdSOFT3275 Act*mdSOFT3275*Institutional*Asset Manager*Implementation*Quantitative Analysis*Fundamental Analysis*Actual*26\340\54\76\10\180\20\0 | mdSOFT3275 | Act*mdSOFT3275*Institutional*Asset | Manager*Implementation*Quantitative | Analysis*Fundamental | Analysis*Actual*26\340\54\76\10\180\20\0
mdSOFT3261 Bud*mdSOFT3261*Institutional*Asset Manager*Implementation*Fundamental Analysis*Quantitative Analysis*Budget*0\415\47\80\10\235\5\38 | mdSOFT3261 | Bud*mdSOFT3261*Institutional*Asset | Manager*Implementation*Fundamental | Analysis*Quantitative | Analysis*Budget*0\415\47\80\10\235\5\38
mdSOFT3213 Bud*mdSOFT3213*Retail*Retail*Wishlist*Fundamental Analysis*None*Budget*0\17\2\1\2\11\1\0 | mdSOFT3213 | Bud*mdSOFT3213*Retail*Retail*Wishlist*Fundamental | Analysis*None*Budget*0\17\2\1\2\11\1\0
mdSOFT3200 Bud*mdSOFT3200*Retail*Retail*Wishlist*Technical Analysis*None*Budget*0\19\2\1\3\10\3\0 | mdSOFT3200 | Bud*mdSOFT3200*Retail*Retail*Wishlist*Technical | Analysis*None*Budget*0\19\2\1\3\10\3\0
mdSOFT3222 Bud*mdSOFT3222*Retail*Retail*Wishlist*Inter-Market Analysis*None*Budget*0\15\2\1\3\8\1\0 | mdSOFT3222 | Bud*mdSOFT3222*Retail*Retail*Wishlist*Inter-Market | Analysis*None*Budget*0\15\2\1\3\8\1\0
mdSOFT3205 Act*mdSOFT3205*Retail*Retail*Wishlist*Technical Analysis*None*Actual*5\7\3\0\1\3\0\0 | mdSOFT3205 | Act*mdSOFT3205*Retail*Retail*Wishlist*Technical | Analysis*None*Actual*5\7\3\0\1\3\0\0
mdSOFT3195 Act*mdSOFT3195*Retail*Retail*Wishlist*Technical Analysis*None*Actual*5\26\4\3\2\13\4\0 | mdSOFT3195 | Act*mdSOFT3195*Retail*Retail*Wishlist*Technical | Analysis*None*Actual*5\26\4\3\2\13\4\0
mdSOFT3192 Act*mdSOFT3192*Retail*Retail*Wishlist*Technical Analysis*None*Actual*3\28\5\0\1\19\3\0 | mdSOFT3192 | Act*mdSOFT3192*Retail*Retail*Wishlist*Technical | Analysis*None*Actual*3\28\5\0\1\19\3\0
mdSOFT3242 Act*mdSOFT3242*Institutional*Broker*Enhancement*Inter-Market Analysis*None*Actual*21\51\10\5\7\23\6\0 | mdSOFT3242 | Act*mdSOFT3242*Institutional*Broker*Enhancement*Inter-Market | Analysis*None*Actual*21\51\10\5\7\23\6\0
mdSOFT3264 Act*mdSOFT3264*Institutional*Retail*Implementation*Fundamental Analysis*Inter-Market Analysis*Actual*3\378\71\95\7\198\7\0 | mdSOFT3264 | Act*mdSOFT3264*Institutional*Retail*Implementation*Fundamental | Analysis*Inter-Market | Analysis*Actual*3\378\71\95\7\198\7\0
mdSOFT3199 Bud*mdSOFT3199*Retail*Retail*Wishlist*Technical Analysis*None*Budget*0\21\3\2\1\14\1\0 | mdSOFT3199 | Bud*mdSOFT3199*Retail*Retail*Wishlist*Technical | Analysis*None*Budget*0\21\3\2\1\14\1\0
mdSOFT3235 Bud*mdSOFT3235*Institutional*Bank*Enhancement*Fundamental Analysis*None*Budget*0\17\3\2\2\7\1\2 | mdSOFT3235 | Bud*mdSOFT3235*Institutional*Bank*Enhancement*Fundamental | Analysis*None*Budget*0\17\3\2\2\7\1\2
mdSOFT3247 Act*mdSOFT3247*Institutional*Bank*Enhancement*Quantitative Analysis*None*Actual*3\39\4\6\6\18\5\0 | mdSOFT3247 | Act*mdSOFT3247*Institutional*Bank*Enhancement*Quantitative | Analysis*None*Actual*3\39\4\6\6\18\5\0
mdSOFT3222 Act*mdSOFT3222*Retail*Retail*Wishlist*Inter-Market Analysis*None*Actual*9\20\4\0\2\12\2\0 | mdSOFT3222 | Act*mdSOFT3222*Retail*Retail*Wishlist*Inter-Market | Analysis*None*Actual*9\20\4\0\2\12\2\0
mdSOFT3274 Bud*mdSOFT3274*Institutional*Broker*Implementation*Quantitative Analysis*Fundamental Analysis*Budget*0\560\80\83\18\319\9\51 | mdSOFT3274 | Bud*mdSOFT3274*Institutional*Broker*Implementation*Quantitative | Analysis*Fundamental | Analysis*Budget*0\560\80\83\18\319\9\51
mdSOFT3211 Bud*mdSOFT3211*Retail*Retail*Wishlist*Fundamental Analysis*None*Budget*0\19\2\1\1\12\3\0 | mdSOFT3211 | Bud*mdSOFT3211*Retail*Retail*Wishlist*Fundamental | Analysis*None*Budget*0\19\2\1\1\12\3\0
mdSOFT3210 Act*mdSOFT3210*Retail*Retail*Wishlist*Fundamental Analysis*None*Actual*5\15\1\2\0\10\2\0 | mdSOFT3210 | Act*mdSOFT3210*Retail*Retail*Wishlist*Fundamental | Analysis*None*Actual*5\15\1\2\0\10\2\0
mdSOFT3253 Bud*mdSOFT3253*Institutional*Retail*Implementation*Technical Analysis*None*Budget*0\583\69\99\20\329\13\53 | mdSOFT3253 | Bud*mdSOFT3253*Institutional*Retail*Implementation*Technical | Analysis*None*Budget*0\583\69\99\20\329\13\53
mdSOFT3257 Act*mdSOFT3257*Institutional*Broker*Implementation*Technical Analysis*None*Actual*14\357\55\84\11\199\8\0 | mdSOFT3257 | Act*mdSOFT3257*Institutional*Broker*Implementation*Technical | Analysis*None*Actual*14\357\55\84\11\199\8\0
mdSOFT3232 Bud*mdSOFT3232*Institutional*Asset Manager*Enhancement*Fundamental Analysis*None*Budget*0\28\4\3\5\10\3\3 | mdSOFT3232 | Bud*mdSOFT3232*Institutional*Asset | Manager*Enhancement*Fundamental | Analysis*None*Budget*0\28\4\3\5\10\3\3
mdSOFT3259 Act*mdSOFT3259*Institutional*Bank*Implementation*Fundamental Analysis*Technical Analysis*Actual*4\354\58\66\16\194\20\0 | mdSOFT3259 | Act*mdSOFT3259*Institutional*Bank*Implementation*Fundamental | Analysis*Technical | Analysis*Actual*4\354\58\66\16\194\20\0
mdSOFT3262 Act*mdSOFT3262*Institutional*Asset Manager*Implementation*Fundamental Analysis*None*Actual*34\360\62\64\7\220\7\0 | mdSOFT3262 | Act*mdSOFT3262*Institutional*Asset | Manager*Implementation*Fundamental | Analysis*None*Actual*34\360\62\64\7\220\7\0
mdSOFT3280 Bud*mdSOFT3280*Institutional*Broker*Implementation*Quantitative Analysis*Inter-Market Analysis*Budget*0\576\86\82\20\329\6\53 | mdSOFT3280 | Bud*mdSOFT3280*Institutional*Broker*Implementation*Quantitative | Analysis*Inter-Market | Analysis*Budget*0\576\86\82\20\329\6\53
mdSOFT3201 Act*mdSOFT3201*Retail*Retail*Wishlist*Technical Analysis*None*Actual*10\21\2\0\2\15\2\0 | mdSOFT3201 | Act*mdSOFT3201*Retail*Retail*Wishlist*Technical | Analysis*None*Actual*10\21\2\0\2\15\2\0
mdSOFT3223 Bud*mdSOFT3223*Retail*Retail*Wishlist*Inter-Market Analysis*None*Budget*0\7\1\1\2\3\0\0 | mdSOFT3223 | Bud*mdSOFT3223*Retail*Retail*Wishlist*Inter-Market | Analysis*None*Budget*0\7\1\1\2\3\0\0
mdSOFT3281 Bud*mdSOFT3281*Institutional*Bank*Implementation*Quantitative Analysis*None*Budget*0\543\69\93\20\299\12\50 | mdSOFT3281 | Bud*mdSOFT3281*Institutional*Bank*Implementation*Quantitative | Analysis*None*Budget*0\543\69\93\20\299\12\50
mdSOFT3244 Bud*mdSOFT3244*Institutional*Asset Manager*Enhancement*Quantitative Analysis*None*Budget*0\32\5\4\5\12\3\3 | mdSOFT3244 | Bud*mdSOFT3244*Institutional*Asset | Manager*Enhancement*Quantitative | Analysis*None*Budget*0\32\5\4\5\12\3\3
mdSOFT3189 Act*mdSOFT3189*Retail*Retail*Wishlist*Technical Analysis*None*Actual*7\25\5\1\1\15\3\0 | mdSOFT3189 | Act*mdSOFT3189*Retail*Retail*Wishlist*Technical | Analysis*None*Actual*7\25\5\1\1\15\3\0
mdSOFT3196 Act*mdSOFT3196*Retail*Retail*Wishlist*Technical Analysis*None*Actual*1\15\1\1\1\11\1\0 | mdSOFT3196 | Act*mdSOFT3196*Retail*Retail*Wishlist*Technical | Analysis*None*Actual*1\15\1\1\1\11\1\0
mdSOFT3212 Act*mdSOFT3212*Retail*Retail*Wishlist*Fundamental Analysis*None*Actual*7\12\1\1\1\8\1\0 | mdSOFT3212 | Act*mdSOFT3212*Retail*Retail*Wishlist*Fundamental | Analysis*None*Actual*7\12\1\1\1\8\1\0
mdSOFT3251 Act*mdSOFT3251*Institutional*Asset Manager*Enhancement*Quantitative Analysis*None*Actual*13\29\2\4\2\18\3\0 | mdSOFT3251 | Act*mdSOFT3251*Institutional*Asset | Manager*Enhancement*Quantitative | Analysis*None*Actual*13\29\2\4\2\18\3\0
mdSOFT3206 Bud*mdSOFT3206*Retail*Retail*Wishlist*Technical Analysis*None*Budget*0\3\1\1\0\1\0\0 | mdSOFT3206 | Bud*mdSOFT3206*Retail*Retail*Wishlist*Technical | Analysis*None*Budget*0\3\1\1\0\1\0\0
mdSOFT3198 Act*mdSOFT3198*Retail*Retail*Wishlist*Technical Analysis*None*Actual*8\11\1\0\1\8\1\0 | mdSOFT3198 | Act*mdSOFT3198*Retail*Retail*Wishlist*Technical | Analysis*None*Actual*8\11\1\0\1\8\1\0
mdSOFT3236 Act*mdSOFT3236*Institutional*Hedge Fund*Enhancement*Fundamental Analysis*None*Actual*20\20\4\2\4\6\4\0 | mdSOFT3236 | Act*mdSOFT3236*Institutional*Hedge | Fund*Enhancement*Fundamental | Analysis*None*Actual*20\20\4\2\4\6\4\0
mdSOFT3248 Act*mdSOFT3248*Institutional*Asset Manager*Enhancement*Quantitative Analysis*None*Actual*5\33\4\5\5\15\4\0 | mdSOFT3248 | Act*mdSOFT3248*Institutional*Asset | Manager*Enhancement*Quantitative | Analysis*None*Actual*5\33\4\5\5\15\4\0
mdSOFT3203 Bud*mdSOFT3203*Retail*Retail*Wishlist*Technical Analysis*None*Budget*0\11\1\1\1\7\1\0 | mdSOFT3203 | Bud*mdSOFT3203*Retail*Retail*Wishlist*Technical | Analysis*None*Budget*0\11\1\1\1\7\1\0
mdSOFT3195 Bud*mdSOFT3195*Retail*Retail*Wishlist*Technical Analysis*None*Budget*0\20\2\2\1\12\3\0 | mdSOFT3195 | Bud*mdSOFT3195*Retail*Retail*Wishlist*Technical | Analysis*None*Budget*0\20\2\2\1\12\3\0
mdSOFT3230 Bud*mdSOFT3230*Institutional*Asset Manager*Enhancement*Technical Analysis*None*Budget*0\38\5\6\4\15\4\4 | mdSOFT3230 | Bud*mdSOFT3230*Institutional*Asset | Manager*Enhancement*Technical | Analysis*None*Budget*0\38\5\6\4\15\4\4
mdSOFT3261 Act*mdSOFT3261*Institutional*Asset Manager*Implementation*Fundamental Analysis*Quantitative Analysis*Actual*42\463\58\102\12\283\8\0 | mdSOFT3261 | Act*mdSOFT3261*Institutional*Asset | Manager*Implementation*Fundamental | Analysis*Quantitative | Analysis*Actual*42\463\58\102\12\283\8\0
mdSOFT3268 Act*mdSOFT3268*Institutional*Broker*Implementation*Inter-Market Analysis*Technical Analysis*Actual*32\394\72\70\23\210\19\0 | mdSOFT3268 | Act*mdSOFT3268*Institutional*Broker*Implementation*Inter-Market | Analysis*Technical | Analysis*Actual*32\394\72\70\23\210\19\0
mdSOFT3256 Bud*mdSOFT3256*Institutional*Asset Manager*Implementation*Technical Analysis*None*Budget*0\315\38\48\13\179\8\29 | mdSOFT3256 | Bud*mdSOFT3256*Institutional*Asset | Manager*Implementation*Technical | Analysis*None*Budget*0\315\38\48\13\179\8\29
mdSOFT3269 Bud*mdSOFT3269*Institutional*Bank*Implementation*Inter-Market Analysis*Fundamental Analysis*Budget*0\557\91\79\13\304\19\51 | mdSOFT3269 | Bud*mdSOFT3269*Institutional*Bank*Implementation*Inter-Market | Analysis*Fundamental | Analysis*Budget*0\557\91\79\13\304\19\51
mdSOFT3220 Bud*mdSOFT3220*Retail*Retail*Wishlist*Fundamental Analysis*None*Budget*0\19\3\1\1\13\1\0 | mdSOFT3220 | Bud*mdSOFT3220*Retail*Retail*Wishlist*Fundamental | Analysis*None*Budget*0\19\3\1\1\13\1\0
mdSOFT3281 Act*mdSOFT3281*Institutional*Bank*Implementation*Quantitative Analysis*None*Actual*24\500\86\89\27\286\12\0 | mdSOFT3281 | Act*mdSOFT3281*Institutional*Bank*Implementation*Quantitative | Analysis*None*Actual*24\500\86\89\27\286\12\0
mdSOFT3198 Bud*mdSOFT3198*Retail*Retail*Wishlist*Technical Analysis*None*Budget*0\13\1\1\2\7\2\0 | mdSOFT3198 | Bud*mdSOFT3198*Retail*Retail*Wishlist*Technical | Analysis*None*Budget*0\13\1\1\2\7\2\0
mdSOFT3271 Act*mdSOFT3271*Institutional*Retail*Implementation*Inter-Market Analysis*Quantitative Analysis*Actual*42\606\102\105\18\365\16\0 | mdSOFT3271 | Act*mdSOFT3271*Institutional*Retail*Implementation*Inter-Market | Analysis*Quantitative | Analysis*Actual*42\606\102\105\18\365\16\0
mdSOFT3220 Act*mdSOFT3220*Retail*Retail*Wishlist*Fundamental Analysis*None*Actual*8\22\1\1\1\17\2\0 | mdSOFT3220 | Act*mdSOFT3220*Retail*Retail*Wishlist*Fundamental | Analysis*None*Actual*8\22\1\1\1\17\2\0
mdSOFT3207 Act*mdSOFT3207*Retail*Retail*Wishlist*Technical Analysis*None*Actual*8\16\2\2\3\8\1\0 | mdSOFT3207 | Act*mdSOFT3207*Retail*Retail*Wishlist*Technical | Analysis*None*Actual*8\16\2\2\3\8\1\0
mdSOFT3284 Bud*mdSOFT3284*Institutional*Asset Manager*Implementation*Quantitative Analysis*Fundamental Analysis*Budget*0\560\79\104\16\305\5\51 | mdSOFT3284 | Bud*mdSOFT3284*Institutional*Asset | Manager*Implementation*Quantitative | Analysis*Fundamental | Analysis*Budget*0\560\79\104\16\305\5\51
mdSOFT3266 Bud*mdSOFT3266*Institutional*Hedge Fund*Implementation*Fundamental Analysis*Inter-Market Analysis*Budget*0\359\56\61\10\192\7\33 | mdSOFT3266 | Bud*mdSOFT3266*Institutional*Hedge | Fund*Implementation*Fundamental | Analysis*Inter-Market | Analysis*Budget*0\359\56\61\10\192\7\33
mdSOFT3221 Bud*mdSOFT3221*Retail*Retail*Wishlist*Inter-Market Analysis*None*Budget*0\22\3\1\1\15\2\0 | mdSOFT3221 | Bud*mdSOFT3221*Retail*Retail*Wishlist*Inter-Market | Analysis*None*Budget*0\22\3\1\1\15\2\0
mdSOFT3279 Act*mdSOFT3279*Institutional*Bank*Implementation*Quantitative Analysis*None*Actual*9\608\112\100\21\355\20\0 | mdSOFT3279 | Act*mdSOFT3279*Institutional*Bank*Implementation*Quantitative | Analysis*None*Actual*9\608\112\100\21\355\20\0
mdSOFT3191 Act*mdSOFT3191*Retail*Retail*Wishlist*Technical Analysis*None*Actual*7\10\1\2\2\3\2\0 | mdSOFT3191 | Act*mdSOFT3191*Retail*Retail*Wishlist*Technical | Analysis*None*Actual*7\10\1\2\2\3\2\0
mdSOFT3265 Bud*mdSOFT3265*Institutional*Bank*Implementation*Fundamental Analysis*None*Budget*0\465\57\68\12\271\14\43 | mdSOFT3265 | Bud*mdSOFT3265*Institutional*Bank*Implementation*Fundamental | Analysis*None*Budget*0\465\57\68\12\271\14\43